## AES MYPRU Development Work
Release date | AES/ MYPRU | JIRA no. | JIRA Link | JIRA Title | Assign To | Repos | Branch | Changes Made | Changes Description | test result | status | Scheduled DEV start Date | Scheduled DEV end Date | Actual DEV start date | Actual DEV end date | DEV final target Date | uat start date | uat end date | pre-prod tgt date | Comment | Review
20230223 | AES | 770 | https://jira.pruconnect.net/browse/PHKLAES-770 | add form code in AES- Submitted Documents and Images | Simon Liao | AES | PPP000022120060-10 |  | 加form id SQL |  | uat sign-off
20230223 | AES | 796 | https://jira.pruconnect.net/browse/PHKLAES-796 | [AES] LFREE day 2- add new form for LFREE prepayment | Simon Liao | AES | PPP000022120060-10 |  |  |  | uat sign-off
20230223 | AES | 802 | https://jira.pruconnect.net/browse/PHKLAES-802 | (PIC Day2)DL add 3 new letters in 已遞交文件及副本 | Simon Liao | AES | PPP000022120060-10 |  |  |  | uat sign-off
20230223 | AES | 810 | https://jira.pruconnect.net/browse/PHKLAES-810 | MKT (AW) - Add Form ID for display Claim Settlement letter | Simon Liao | AES | PPP000022120060-10 |  |  |  | uat sign-off
20230223 | AES | 805 | https://jira.pruconnect.net/browse/PHKLAES-805 | MKT (AW) - Add remark in My Achievement - Projected Production Commission plus Case Count Modifier | Heaton Liu | SAES | PPP0000221200600 |  |  |  | uat sign-off
20230223 | MYPRU | 1170 | https://jira.pruconnect.net/projects/PHKLMYPRUDENTIAL/issues/PHKLMYPRUDENTIAL-1170?filter=allissues | [SR02238486] Fix mobile no. issue to avoid customer failed to receive SMS (suppress leading zero) | Heaton Liu | AESSVC | SR02238486 |  |  |  | uat sign-off
20230223 | MYPRU | 1171 | https://jira.pruconnect.net/projects/PHKLMYPRUDENTIAL/issues/PHKLMYPRUDENTIAL-1171?filter=allissues | [SR02238486] Allow corporate client to use CI no. for myPru registration | Simon Liao | SCWS | SR02238486 | WebContent/WEB-INF/message/member/view_en.properties changed WebContent/WEB-INF/message/member/view_zh.properties changed | 添加新的变量用于显示 |  | uat sign-off
20230223 | MYPRU | 1171 | https://jira.pruconnect.net/projects/PHKLMYPRUDENTIAL/issues/PHKLMYPRUDENTIAL-1171?filter=allissues | [SR02238486] Allow corporate client to use CI no. for myPru registration | Simon Liao | APPSVC | SR02238486 | a074-appsvc\src\com\pru\hk\admin\maintmem\spring\bean\RegisterMemberBusinessBean.java a074-appsvc\src\com\pru\hk\client\eai\ClientEai.java a074-appsvc\src\com\pru\hk\client\eai\impl\ClientEaiImpl.java | APPSVC添加EAI接口直接调用prulife DB的 sql = "select client_cd from cdb_id_doc where id_no like concat(?,'%') and status = 'A'"; 返回字段给service去判断， 这样用户输入的注册id可以多查找这个sql， 如果有，就不报错说id没找到 |  | uat sign-off
20230320 | MYPRU | 1161 | https://jira.pruconnect.net/browse/PHKLMYPRUDENTIAL-1161 | myPRU to support oversea number (but not only accept 8 digit hk no. ) | Vito Yu | SCWS | SR02214575-support_mainland_number | src/com/pru/hk/web/controller/scws/member/EbRegistrationController.java changed WebContent/WEB-INF/view/member/registration/eb/stepEbee2.jsp changed WebContent/WEB-INF/message/member/view_en.properties changed WebContent/WEB-INF/message/member/view_zh.properties changed | 前端添加area code显示，逻辑不用修改 | ready | assigned back to user | 2023-02-27 | 2023-02-27 | 2023-02-27 | 2023-02-27 |  | 2023-02-27 |  | 2023-02-27
20230320 | MYPRU | 1158 | https://jira.pruconnect.net/browse/PHKLMYPRUDENTIAL-1158 | Delightful Life (DL) Day 2 - add remark for SA after delightful reward has been paid | Vito Yu | SESV | 220601700 | src/com/pru/hk/mypru/adapter/ws/soap/SoapPolicySummaryAdapter.java changed src/com/pru/hk/mypru/adapter/ws/PolicySummaryAdapter.java changed src/com/pru/hk/mypru/facade/PolicySummaryFacade.java changed src/com/pru/hk/mypru/service/PolicyService.java changed src/com/pru/hk/mypru/web/controller/LifePolicyController.java changed stub/com/pru/hk/mypru/stub/policy/life/ws/PolicySummarySoapService.java changed WebContent/WEB-INF/message/mypru/view_en.properties changed WebContent/WEB-INF/message/mypru/view_zh.properties changed WebContent/WEB-INF/message/policydetail/view_en.properties changed WebContent/WEB-INF/message/policydetail/view_zh.properties changed WebContent/WEB-INF/view/mypru/policy/detail/my_coverage.jsp changed WebContent/WEB-INF/view/mypru/policy/fvi/fvi_cm_master.jsp changed WebContent/WEB-INF/view/mypru/policy/fvi/fvi_master.jsp changed WebContent/WEB-INF/view/mypru/policy/savingsProtectionRevamp.jsp changed | 对于3个JIRA提到的地方，首页saving， policy detail, FVI, 后面只有当prod_cd 是EL ELP， 还有3个条件都满足，加上remark,其中一个条件来源于prulife的一个接口，所以代码还添加了新接口用于调用这个来获取reward paid out indicator |  | assigned back to user | 2023-03-10 | 2023-03-10 | 2023-03-10 | 2023-03-10 |  | 2023-03-10 |  | 2023-03-10 | postpone to 0331 product issue, call sp need delete uat | OK
20230320 | MYPRU | 1158 | https://jira.pruconnect.net/browse/PHKLMYPRUDENTIAL-1158 | Delightful Life (DL) Day 2 - add remark for SA after delightful reward has been paid | Vito Yu | AESSVC | 220601700 220601700-01(Latest one) | src/com/pru/hk/client/dao/impl/ClientDaoInformixImpl.java changed src/com/pru/hk/client/dao/ClientDaoInformix.java changed src/com/pru/hk/policy/life/dao/impl/PolicyDaoInformixImpl.java changed src/com/pru/hk/policy/life/dao/PolicyDaoInformix.java changed src/com/pru/hk/policy/life/service/PolicySummaryService.java changed src/com/pru/hk/policy/life/spring/bean/PolicyBusinessBean.java changed src/com/pru/hk/policy/life/spring/bean/PolicyControllorBusinessBean.java changed src/com/pru/hk/policy/life/ws/soap/impl/PolicySummarySoapServiceImpl.java changed src/com/pru/hk/policy/life/ws/PolicySummarySoapService.java changed" | 添加调用 call prulife@prulifeu1t:sp_chk_rtb_payout(?) 语句 |  | assigned back to user | 2023-03-10 | 2023-03-10 | 2023-03-10 | 2023-03-10 |  | 2023-03-10 |  | 2023-03-10 | postpone to 0331 product issue, call sp need delete uat | OK
20230331 | AES | 797 | https://jira.pruconnect.net/browse/PHKLAES-797 | PIC- EGIP - AES enquiry page | Simon Liao | AES | 220700600-10 | N/A |  |  | assigned back to user | 2023-02-27 | 2023-02-27 | 2023-02-27 | 2023-02-27 |  | 2023-02-27 |  | 2023-02-27
20230331 | AES | 798 | https://jira.pruconnect.net/browse/PHKLAES-798 | PIC-EGIP - AES Basic Info page | Vito Yu | SAES | 220700600-10 | WebContent/WEB-INF/view/proposal_policy/policy_details.jsp WebContent/WEB-INF/message/aes/locale_zh.propertiesM WebContent/WEB-INF/message/aes/locale_en.properties | 前端加新的关于EGIP的remark， 同时， 需要参考有EGI的代码， 部分地方就要加上EGIP |  | assigned back to user | 2023-03-02 | 2023-03-02 | 2023-03-02 | 2023-03-02 |  | 2023-03-02 |  | 2023-03-02 |  | OK
20230331 | AES | 798 | https://jira.pruconnect.net/browse/PHKLAES-798 | PIC-EGIP - AES Basic Info page | Vito Yu | AESSVC | 220700600-10 | src/com/pru/hk/policy/life/dao/impl/LifePolicyDaoInformixImpl.java | 需要参考有EGI的代码， 部分地方就要加上EGIP |  | assigned back to user | 2023-03-02 | 2023-03-02 | 2023-03-02 | 2023-03-02 |  | 2023-03-02 |  | 2023-03-02 |  | OK
20230331 | AES | 801 | https://jira.pruconnect.net/browse/PHKLAES-801 | [PIC] EGIP - Alteration Quotation | Vito Yu | SAES | N/A | N/A | 因为数据来源于prulife， 所以没修改 |  | assigned back to user | 2023-03-02 | 2023-03-02 | 2023-03-02 | 2023-03-02 |  | 2023-03-02 |  | 2023-03-02 |  | OK
20230331 | AES | 800 | https://jira.pruconnect.net/browse/PHKLAES-800 | [PIC] EGIP - Financial Overview | Heaton Liu | AES | 220700600-10 | ARMLET-IFX/220700600-10.sh created store/220700600-10.lst created store/220700600-10.sql created | 加sql insert aes_tbl_config 'EGIP' | ready | assigned back to user | 2023-03-02 | 2023-03-02 | 2023-03-02 | 2023-03-02 |  | 2023-03-02 |  | 2023-03-02 |  | OK
20230331 | AES | 809 | https://jira.pruconnect.net/browse/PHKLAES-809 | [PIC] EGIP- add new form for EGIP prepayment | Simon Liao | AES | 220700600-10 | store/220700600-20.sql created | 加sql insert form ID |  | assigned back to user | 2023-02-23 | 2023-02-23 | 2023-02-23 | 2023-02-23 |  | 2023-02-23 |  | 2023-02-23
20230331 | AES | 813 | https://jira.pruconnect.net/browse/PHKLAES-813 | [PIC] Adding new field to AES basic info, Premium Information to display the Premium Prepayment Option | Heaton Liu | SAES | 220700600-10 | WebContent/WEB-INF/view/proposal_policy/policy_details.jsp changed WebContent/WEB-INF/message/aes/locale_en.properties changed WebContent/WEB-INF/message/aes/locale_zh.properties changed | 添加一个新字段，本来prulife写了新的sp来返回，现在不用，直接用原来的life_policy.praiInfo.prepaidDiscountPromotionFlag， 需要判断'Y' 'N' '' 三种情况 | ready | assigned back to user | 2023-03-07 | 2023-03-07 | 2023-03-07 | 2023-03-07 |  | 2023-03-07 |  | 2023-03-07
20230331 | AES | 833 | https://jira.pruconnect.net/browse/PHKLAES-833 | PIC AES- EGIP missing remarks under Benefit information | Heaton Liu | SAES | N/A | N/A | JIRA798 bug, due to clean up happened on 8 March, changes of JIRA798 got deleted in was9, user test this on 9 March, so created JIRA833 as the bug for JIRA798, but JIRA798 source codes was put to was9 10 March. |  | assigned back to user | 2023-03-13 | 2023-03-13 | 2023-03-13 | 2023-03-13 |  | 2023-03-13 |  | 2023-03-13
20230331 | MYPRU | 1175 | https://jira.pruconnect.net/browse/PHKLMYPRUDENTIAL-1175 | [PPP220700600] PIC New Product – EGIP | Simon Liao | SESV | 220700600-10 | sv_hk/store/informix/f created esv_hk/store/informix/pre-production.lst changed esv_hk/store/informix/was9_common.lst changed WebContent/WEB-INF/message/policydetail/view_en.properties changed WebContent/WEB-INF/message/policydetail/view_zh.properties changed WebContent/WEB-INF/view/mypru/policy/detail/monthly_income _table.jsp changed WebContent/WEB-INF/view/mypru/policy/detail/my_coverage.jsp changed WebContent/WEB-INF/view/mypru/policy/detail/policy_basic.jsp changed WebContent/WEB-INF/view/mypru/policy/financialSection/monthlyIncomeSection/monthlyIncome_section_master.jsp changed WebContent/WEB-INF/view/mypru/policy/financialSection/monthlyIncomeSection/monthlyIncome_section_template_c.jsp changed WebContent/WEB-INF/view/mypru/policy/financialSection/accumulationaccount.jsp changed WebContent/WEB-INF/view/mypru/policy/financialSection/basic_value.jsp changed WebContent/WEB-INF/view/mypru/policy/financialSection/cv_trad.jsp changed WebContent/WEB-INF/view/mypru/policy/financialSection/trad_policy.jsp changed | SQL SESV 模板 加入新的remark for EGIP, 需要参考有EGI的代码， 部分地方就要加上EGIP | ready | assigned back to user | 2023-03-03 | 2023-03-03 | 2023-03-03 | 2023-03-03 |  | 2023-03-03 |  | 2023-03-03
20230331 | MYPRU | 1175 | https://jira.pruconnect.net/browse/PHKLMYPRUDENTIAL-1175 | [PPP220700600] PIC New Product – EGIP | Simon Liao | AESSVC | 220700600-10 | src/com/pru/hk/policy/life/dao/impl/LifePolicyDaoInformixImpl.javaMODIFIED changed src/com/pru/hk/policy/life/spring/bean/FinancialBusinessBean.java changed src/com/pru/hk/policy/life/to/ProdSeries.java changed | 需要参考有EGI的代码， 部分地方就要加上EGIP | ready | assigned back to user | 2023-03-03 | 2023-03-03 | 2023-03-03 | 2023-03-03 |  | 2023-03-03 |  | 2023-03-03
20230331 | MYPRU | 1253 | https://jira.pruconnect.net/browse/PHKLMYPRUDENTIAL-1253 | Put "Terminal dividend" and "Total dividend balance" under table Financial Summary > Basic Plan Values | Heaton Liu | SESV | 220700600-10 | WebContent/WEB-INF/view/mypru/policy/financialSection/cv_trad.jsp changed WebContent/WEB-INF/view/mypru/policy/financialSection/basic_value.jspchanged | 把cv_trade.jsp里面的 Terminal dividend" and "Total dividend balance" 把开头的很多条件删除掉直接挪到/basic_value.jsp 的 Basic Plan Values | ready | assigned back to user | 2023-03-03 | 2023-03-03 | 2023-03-03 | 2023-03-03 |  | 2023-03-03 |  | 2023-03-03 |  | OK
20230331 | MYPRU | 1246 | https://jira.pruconnect.net/browse/PHKLMYPRUDENTIAL-1246 | Delightful Life (DL) Day 2 - cannot show SA remark | Vito Yu | SESV | N/A | 已经包含在JIRA1158 |  | ready | assigned back to user | 2023-03-21 | 2023-03-21 | 2023-03-21 | 2023-03-21 |  | 2023-03-21 |  | 2023-03-21
20230417 | MYPRU | 1255 | https://jira.pruconnect.net/browse/PHKLMYPRUDENTIAL-1255 | EGIP - not showing Contingent Life Assured under Policy Details | Simon Liao | AESSVC | SR02272876 | src/com/pru/hk/policy/life/dao/impl/EServicingDaoInformixImpl.java changed | 把2022年7月的修改回复回来，这样可以看到role 'M' contigent life assured | ready | assigned back to user | 2023-03-29 | 2023-03-29 | 2023-03-29 | 2023-03-29 |  | 2023-03-29 |  | 2023-03-29
20230417 | AES | 819 | https://jira.pruconnect.net/browse/PHKLAES-819 | MKT (AW) - Add field to display Contingent Life Assured in Policy details | Vito Yu | SAES | SR02272876 | WebContent/WEB-INF/view/proposal_policy/policy_details.jsp | jsp页面添加client role 条件 "CONTINGENT LIFE ASSURED" | ready | assigned back to user | 2023-03-29 | 2023-03-29 | 2023-03-29 | 2023-03-29 |  | 2023-03-29 |  | 2023-03-29
20230417 | AES | 819 | https://jira.pruconnect.net/browse/PHKLAES-819 | MKT (AW) - Add field to display Contingent Life Assured in Policy details | Vito Yu | AESSVC | SR02272876 | src/com/pru/hk/policy/life/dao/impl/EServicingDaoInformixImpl.java changed src/com/pru/hk/policy/life/spring/bean/LifePolicyBusinessBean.java changed src/com/pru/hk/to/policy/life/LifePolicyPersonnelTO.java changed | 添加条件 ClientRole.equalsIgnoreCase("CONTINGENT LIFE ASSURED") | ready | assigned back to user | 2023-03-29 | 2023-03-29 | 2023-03-29 | 2023-03-29 |  | 2023-03-29 |  | 2023-03-29
20230417 | MYPRU | 1019 | https://jira.pruconnect.net/projects/PHKLMYPRUDENTIAL/issues/PHKLMYPRUDENTIAL-1019?filter=allissues | EGA FVI page | Vito Yu | SESV | PPP20220113-EGA | esv_hk/store/informix/PPP20220113-EGA.sql | 在table fvi_template_config添加EGA prod code | ready | assigned back to user | 2023-03-30 | 2023-03-30 | 2023-03-30 | 2023-03-30 |  | 2023-03-30 |  | 2023-03-30
20230417 | MYPRU | 1237 | https://jira.pruconnect.net/projects/PHKLMYPRUDENTIAL/issues/PHKLMYPRUDENTIAL-1237?filter=myopenissues | [PPP221201301] Update SBR fund name and remark | Simon Liao | SESV | 221201301-10 | WebContent/WEB-INF/message/mypru/view_en.properties changed WebContent/WEB-INF/message/mypru/view_zh.properties changed WebContent/WEB-INF/view/main/fund_select_overlay.jsp changed WebContent/WEB-INF/view/main/fund_select_overlay_remark.jsp changed | add 'SBR' fund name in jsp | ready | assigned back to user | 2023-03-29 | 2023-03-29 | 2023-03-29 | 2023-03-29 |  | 2023-03-29 |  | 2023-03-29
20230424 | MYPRU | 1336 | https://jira.pruconnect.net/projects/PHKLMYPRUDENTIAL/issues/PHKLMYPRUDENTIAL-1336?filter=myopenissues | IN02321918 fix FVI error | Heaton Liu | AESSVC | IN02321918 | PolicyDaoInformixImpl.java | String sql = "call prulife@prulifeu1t:sp_chk_rtb_payout(?)";---delete this line. String dbName = ""; String sql = ""; dbName = commonDao.getInformixDbName().trim(); if(PRUConstant.PROD_DB_PRUPP4.equals(dbName)) { sql = "call prulife@prulifep4t:sp_chk_rtb_payout(?)"; } else if (PRUConstant.UAT_DB_PRUPU1.equals(dbName)) { sql = "call prulife@prulifeu1t:sp_chk_rtb_payout(?)"; }else { sql = "call prulife@prulifed1t:sp_chk_rtb_payout(?)"; } | ready | assigned back to user | 2023-04-21 | 2023-04-21 | 2023-04-21 | 2023-04-21 |  | 2023-04-21 |  | 2023-04-21
20230427 | AES | 789 | https://jira.pruconnect.net/browse/PHKLAES-789 | PIC-POPI - AES enquiry page | Simon Liao | SAES | N/A | N/A | 1. POPI drop list is from prulife, AFYP logic already exists, no source code changes. 2. the second point, AFYP is from DB SP, there is no prod code constraint, so no source code changes. 3. detail analysis: AFYP in "My Business" searching tab result is from search_policy.jsp's line 1052 <div id="result_container"> and this items="${result_list}" is populated in ProposalPolicyController.java SAES policyResultFinalList object which is from searchPolicyAdvance method in the calling process, and finally it comes from line 5020 call sp_aes_adv_pol_list('"+ …) in LifePolicyDaoInformixImpl.java in AESSVC repository. 4.policy.setAfyp(rs.getBigDecimal(21)); 5. now AFYP is 390000,select modal_prem, pay_mode, ccy from pol_basic where pol_no = '000020207626'; see it is 500000, modal premium 'S', ccy is USD, select * from aux_currency where ccy_cd = 'USD'; see ex_api_rate is 7.8, so AFYP = 500000 X 7.8 / 10 = 390000 | ready | assigned back to user | 2023-03-28 | 2023-03-28 | 2023-03-28 | 2023-03-28 |  | 2023-03-28 |  | 2023-03-28
20230427 | AES | 790 | https://jira.pruconnect.net/browse/PHKLAES-790 | PIC-POPI- AES Basic Info page | Heaton Liu | AES | 220700700-10 | ARMLET-IFX/220700700-10.sh created store/220700700-10.lst created store/220700700-10.sql created | 頁面上的Benefit Option and Product Feature 沒有顯示,因爲call了以下sp沒找到數據導致 policyDetailDynamicCtlList = AESFacade.getAESDynamicCtlList("policy.detail", prodCd); 只需要在加這個數據到table裏面,以上sp就會顯示數據,然而頁面就會出來了 INSERT INTO aes_tbl_config VALUES ('policy.detail','totalPremiumPaid',0,'POPI','','220700700-10',current); | ready | assigned back to user | 2023-03-20 | 2023-03-20 | 2023-03-20 | 2023-03-20 |  | 2023-03-20 |  | 2023-03-20
20230427 | AES | 791 | https://jira.pruconnect.net/browse/PHKLAES-791 | PIC-POPI- Financial Overview | Heaton Liu | AES | 220700700-10 | ARMLET-IFX/220700700-10.sh created store/220700700-10.lst created store/220700700-10.sql created | add sql for product code 'POPI' | ready | assigned back to user | 2023-03-20 | 2023-03-20 | 2023-03-20 | 2023-03-20 |  | 2023-03-20 |  | 2023-03-20
20230427 | AES | 791 | https://jira.pruconnect.net/browse/PHKLAES-791 | PIC-POPI- Financial Overview | Heaton Liu | AESSVC | 220700700-10 | src/com/pru/hk/policy/life/spring/bean/LifePolicyBusinessBean.java Changed | if (lifePolicyTO.isAApolicy() ¦¦ "POPI".equals(lifePolicyTO.getProductCode()) ¦¦ | ready | assigned back to user | 2023-03-20 | 2023-03-20 | 2023-03-20 | 2023-03-20 |  | 2023-03-20 |  | 2023-03-20 | #NAME?
20230427 | AES | 792 | https://jira.pruconnect.net/browse/PHKLAES-792 | PIC-POPI - AES Alteration Quotation | Heaton Liu | SAES | N/A | N/A | 1. record, not mentioned. 2. 看下程序，在保單更改詳情 alteration quotation， 是否和PEPI一樣， 程序看有沒有 對prod_cd 進行 PEPI 判斷或篩選，如果有，需要加上POPI， 加入沒有，就不用改程序。 3. Heaton: 前端 后端 MYPRU 系统 ---SESV ----AESSVC AES 系统 ---SAES ---AESSVC ----AES---------¦ JIRA792 1. AES系统， 保单详情 policy_details.jsp ---SAES 在显示 2. 点击 保单变更详情，触发: a class="aeslink" , 访问下面controller <p><a class="aeslink" url="https://${aes_url}/aes/AESServlet?module=proposalpolicy&type=iPC&purpose=getQuotationTypes&pol_no=${policy_no}&agentCd=${agent_cd}&abranchCd=${branchCd}"><spring:message code="pru.aes.title.alterationQuotation"/></a></p> ¦ ¦ 3.上面被访问后， AESServlet代码， 里面框架就会访问到 --->aesService.xml (---AES repository) 入口,根據 getQuotationTypes定位到PolicyServiceBean這個類 -------------------------aesService.xml --------------------------------------------------------------- <getQuotationTypes id="service" type="private">com.pru.aes.proposalpolicy.service.PolicyServiceBean</getQuotationTypes> ------------------------------------------------------------------------------------------------------------------------------ 4. PolicyServiceBean.java 根據getQuotationTypes关键字 定位到context = getQuotationTypes(context); getQuotationTypes(context)該方法裏面核心就這兩個方法 context = getPolicy(context); // 進去找子方法可以找到QuotationTypes.jsp那個form的數據源頭 policy = PolicyDBHelper.getPolicy(context, agentCd, pol_no); ¦----> call sp_aes_get_pol(?, ?) 入參policyNo,agentCd------没有任何对prod code 的判断 -- policy = PolicyDBHelper.getQuotationTypes(context, policy, pol_no);//下面sp是QuotationTypes.jsp下拉框數據源頭 ¦-->call sp_aes_quot_types(?)//入參polNo---------没有任何对prod code 的判断 最終所有數據封裝進Policy對象放進context 5. 上面2个方法返回的数据， 被封装到context后，从下面jsp 显示出来： QuotationTypes.jsp --AES 頁面分爲兩部分數據,一個form,一個下拉框,下面介紹怎麽定位 页面这样取到数据： <% Context context = (Context)request.getAttribute("context"); %> policy = (Policy)obj; 后面就封装数据到前端jsp显示 6. 所以不用修改 | ready | assigned back to user | 2023-03-24 | 2023-03-24 | 2023-03-24 | 2023-03-24 |  | 2023-03-24 |  | 2023-03-24
20230427 | AES | 803 | https://jira.pruconnect.net/browse/PHKLAES-803 | PIC-POPI-add form code in AES- Submitted Documents and Images | Simon Liao | AES | 220700700-10 | 220700700-20.sql |  |  | assigned back to user | 2023-03-24 | 2023-03-24 | 2023-03-24 | 2023-03-24 |  | 2023-03-24 |  | 2023-03-24
20230427 | MYPRU | 1156 | https://jira.pruconnect.net/browse/PHKLMYPRUDENTIAL-1156 | [PPP220700700] PIC New Product – POPI https://jira.pruconnect.net/browse/PHKLPOPI-54 | Vito Yu | SESV | 220700700-10 |  |  |  | assigned back to user | 2023-04-14 | 2023-04-14 | 2023-04-14 | 2023-04-14 |  | 2023-04-14 |  | 2023-04-14
20230427 | MYPRU | 1156 | https://jira.pruconnect.net/browse/PHKLMYPRUDENTIAL-1156 | [PPP220700700] PIC New Product – POPI https://jira.pruconnect.net/browse/PHKLPOPI-54 | Vito Yu | AESSVC | 220700700-10 |  |  |  | assigned back to user | 2023-04-14 | 2023-04-14 | 2023-04-14 | 2023-04-14 |  | 2023-04-14 |  | 2023-04-14
20230427 | MYPRU | 1156 | https://jira.pruconnect.net/browse/PHKLMYPRUDENTIAL-1156 | [PPP220700700] PIC New Product – POPI https://jira.pruconnect.net/browse/PHKLPOPI-54 | Vito Yu | AES | 220700700-10 |  |  |  | assigned back to user | 2023-04-14 | 2023-04-14 | 2023-04-14 | 2023-04-14 |  | 2023-04-14 |  | 2023-04-14
20230427 | MYPRU | 1156 | https://jira.pruconnect.net/browse/PHKLMYPRUDENTIAL-1156 | [PPP220700700] PIC New Product – POPI https://jira.pruconnect.net/browse/PHKLPOPI-55 | Heaton Liu | SESV | 220700700-10 | WebContent/WEB-INF/view/mypru/portfolioDashboard/index.jsp changed src/com/pru/hk/mypru/common/SesvConstants.java changed src/com/pru/hk/mypru/web/controller/PortfolioDashboardController.java changed | add product code 'POPI' | ready | assigned back to user | 2023-03-31 | 2023-03-31 | 2023-03-31 | 2023-03-31 |  | 2023-03-31 |  | 2023-03-31
20230427 | MYPRU | 1156 | https://jira.pruconnect.net/browse/PHKLMYPRUDENTIAL-1156 | [PPP220700700] PIC New Product – POPI https://jira.pruconnect.net/browse/PHKLPOPI-56 | Simon Liao |  | N/A | N/A | No source code changes |  | assigned back to user | 2023-04-03 | 2023-04-03 | 2023-04-03 | 2023-04-03 |  | 2023-04-03 |  | 2023-04-03
20230427 | MYPRU | 1156 | https://jira.pruconnect.net/browse/PHKLMYPRUDENTIAL-1156 | [PPP220700700] PIC New Product – POPI https://jira.pruconnect.net/browse/PHKLPOPI-57 | Simon Liao |  | N/A | N/A | No source code changes |  | assigned back to user | 2023-04-03 | 2023-04-03 | 2023-04-03 | 2023-04-03 |  | 2023-04-03 |  | 2023-04-03
20230427 | MYPRU | 1156 | https://jira.pruconnect.net/browse/PHKLMYPRUDENTIAL-1156 | [PPP220700700] PIC New Product – POPI https://jira.pruconnect.net/browse/PHKLPOPI-58 | Vito Yu |  | N/A | N/A | No source code changes |  | assigned back to user | 2023-04-03 | 2023-04-03 | 2023-04-03 | 2023-04-03 |  | 2023-04-03 |  | 2023-04-03
20230427 | MYPRU | 1156 | https://jira.pruconnect.net/browse/PHKLMYPRUDENTIAL-1156 | [PPP220700700] PIC New Product – POPI https://jira.pruconnect.net/browse/PHKLPOPI-59 | Heaton Liu |  | N/A | N/A | No source code changes |  | assigned back to user | 2023-04-03 | 2023-04-03 | 2023-04-03 | 2023-04-03 |  | 2023-04-03 |  | 2023-04-03
20230427 | MYPRU | 1156 | https://jira.pruconnect.net/browse/PHKLMYPRUDENTIAL-1156 | [PPP220700700] PIC New Product – POPI https://jira.pruconnect.net/browse/PHKLPOPI-125 | Heaton Liu | SESV | 220700700-10 | src/com/pru/hk/mypru/adapter/ws/soap/SoapPolicyDetailAdapter.javaMODIFIED src/com/pru/hk/mypru/adapter/ws/PolicyDetailAdapter.javaMODIFIED src/com/pru/hk/mypru/facade/PolicyDetailFacade.javaMODIFIED src/com/pru/hk/mypru/web/controller/LifePolicyController.javaMODIFIED stub/com/pru/hk/mypru/stub/policy/life/ws/AAPolicyValueForBankAcct.javaADDED stub/com/pru/hk/mypru/stub/policy/life/ws/PolicyDetailSoapService.javaMODIFIED WebContent/WEB-INF/message/policydetail/view_en.propertiesMODIFIED WebContent/WEB-INF/message/policydetail/view_zh.propertiesMODIFIED WebContent/WEB-INF/view/mypru/policy/financialSection/aa_policy_value_section.jspMODIFIED |  | ready | assigned back to user | 2023-04-14 | 2023-04-14 | 2023-04-14 | 2023-04-14 |  | 2023-04-14 |  | 2023-04-14 | call sp need delete uat
20230427 | MYPRU | 1156 | https://jira.pruconnect.net/browse/PHKLMYPRUDENTIAL-1156 | [PPP220700700] PIC New Product – POPI https://jira.pruconnect.net/browse/PHKLPOPI-125 | Heaton Liu | AESSVC | 220700700-10 | src/com/pru/hk/policy/life/dao/impl/PolicyDaoInformixImpl.javaMODIFIED src/com/pru/hk/policy/life/dao/PolicyDaoInformix.javaMODIFIED src/com/pru/hk/policy/life/service/PolicyDetailService.javaMODIFIED src/com/pru/hk/policy/life/spring/bean/FinancialBusinessBean.javaMODIFIED src/com/pru/hk/policy/life/spring/bean/PolicyControllorBusinessBean.javaMODIFIED src/com/pru/hk/policy/life/to/AAPolicyValueForBankAcct.javaADDED src/com/pru/hk/policy/life/ws/soap/impl/PolicyDetailSoapServiceImpl.javaMODIFIED src/com/pru/hk/policy/life/ws/PolicyDetailSoapService.javaMODIFIED |  | ready | assigned back to user | 2023-04-14 | 2023-04-14 | 2023-04-14 | 2023-04-14 |  | 2023-04-14 |  | 2023-04-14 | call sp need delete uat
20230427 | MYPRU | 1274 | https://jira.pruconnect.net/browse/PHKLMYPRUDENTIAL-1274 | PEPI fund switching production issue | Simon Liao | SESV | PHKLMYPRUDENTIAL-1274 | view/mypru/switchExistingInvestmentChoices/view.jsp changed |  |  | assigned back to user | 2023-04-24 | 2023-04-24 | 2023-04-24 | 2023-04-24 |  | 2023-04-24 |  | 2023-04-24
20230518 | AES | 820 | https://jira.pruconnect.net/projects/PHKLAES/issues/PHKLAES-820?filter=myopenissues | PIC-CIM3- AES enquiry page | Simon Liao | AES | N/A | N/A | 不用改的原因是因为下拉框是从prulife同步过来的 就这张表select * from prulife@prulifeu1t:prod_mast | ready | assigned back to user | 2023-04-12 | 2023-04-14 | 2023-04-14 | 2023-04-14 |  | 2023-05-04 | 2023-05-15 | 2023-05-16 | refer to 'CIM2'
20230518 | AES | 821 | https://jira.pruconnect.net/projects/PHKLAES/issues/PHKLAES-821?filter=myopenissues | PIC-CIM3 - AES Basic Info page | Vito Yu | AES | N/A | N/A | JIRA要求1： 不用改， 因为policy_details.jsp 里面 line 2123 benefitInfo 这个table， 下面的remark， 没有CIM2 的参考，remark来源于table JIRA要求2: benefit option， 没有prod code的条件需要加 | ready |  | 2023-04-12 | 2023-04-14 | 2023-04-18 | 2023-04-18 |  | 2023-05-04 | 2023-05-15 | 2023-05-16 | refer to 'CIM2'
20230518 | AES | 823 | https://jira.pruconnect.net/projects/PHKLAES/issues/PHKLAES-823?filter=myopenissues | PIC-CIM3- Financial Overview | Heaton Liu | AES | 221201000-10 | ARMLET-IFX/221201000-10.sh created store/221201000-10.lst created store/221201000-10.sql created | Attention: missing store/sp_aes_benf_desc.sql see JIRA917 add sql insert aes_tbl_config 'CIM3' 'CIM3H' 'CIM3M' 'CIM3HM', for UI webpage searching and display | re-test ok | assigned back to user | 2023-04-12 | 2023-04-14 | 2023-04-13 | 2023-04-13 |  | 2023-05-04 | 2023-05-15 | 2023-05-16 | refer to JIRA791
20230518 | AES | 823 | https://jira.pruconnect.net/projects/PHKLAES/issues/PHKLAES-823?filter=myopenissues | PIC-CIM3- Financial Overview | Heaton Liu | SAES | 221201000-10 | WebContent/WEB-INF/view/proposal_policy/policy_details.jsp changed | add all product codes, so as to display remarks 还需要修改另外2个地方，否则remark的主体不会显示 "*" | re-test ok | assigned back to user | 2023-04-12 | 2023-04-14 | 2023-04-13 | 2023-04-13 |  | 2023-05-04 | 2023-05-15 | 2023-05-16 | refer to JIRA791
20230518 | AES | 823 | https://jira.pruconnect.net/projects/PHKLAES/issues/PHKLAES-823?filter=myopenissues | PIC-CIM3- Financial Overview | Heaton Liu | AESSVC | 221201000-10 | src/com/pru/hk/policy/life/dao/impl/LifePolicyDaoInformixImpl.java changd src/com/pru/hk/policy/life/spring/bean/LifePolicyBusinessBean.java changed | first java is for "TerminalBonusFaceValue displa", the 2nd java is for "已付讫的赔偿总额", 这个数据从SP 来 | re-test ok | assigned back to user | 2023-04-12 | 2023-04-14 | 2023-04-13 | 2023-04-13 |  | 2023-05-04 | 2023-05-15 | 2023-05-16 | refer to JIRA791
20230518 | AES | 824 | https://jira.pruconnect.net/projects/PHKLAES/issues/PHKLAES-824?filter=myopenissues | PIC-CIM3- AES Alteration Quotation | Heaton Liu | AES | N/A | N/A | 829 ---没任何代码或sql的修改。 https://jira.pruconnect.net/browse/PHKLAES-829 BCIM3 Alteration Quotation: From JIRA On AES > Alteration Quotation screen, should proceed the Alternation Quotation as the followings: Quotation type Description Plan [BCIM3] DECSUM Decrease Sum Assured allow INCSUM Increase Sum Assured Not Allowed (unless during Cooling-off period) CHMODE Mode Change allow ADDRID Add Rider allow REVIVAL Revival allow x REDATE Revival by re-dating Not allow 824 ---没任何代码或sql的修改。 From JIRA https://jira.pruconnect.net/browse/PHKLAES-824 CIM3 Quotation type Description Plan [CIM3] DECSUM Decrease Sum Assured allow INCSUM Increase Sum Assured Not Allowed (unless during Cooling-off period CHMODE Mode Change allow ADDRID Add Rider allow REVIVAL Revival allow x REDATE Revival by re-dating Not allow 824和829 一樣 ----------------- 1 下拉框call 了這個sp policy = PolicyDBHelper.getQuotationTypes(context, policy, pol_no);//下面sp是QuotationTypes.jsp下拉框數據源頭 call sp_aes_quot_types(?)//入參polNo 回來的Y就會顯示,其中REVIVAL是N,但是我們需要Y 問了alex 調查后,他說是因爲這個存儲過程sp_aes_tiu_pobas 裏面有個policy status判斷REVIVAL,如下: 2 其中REVIVAL這個值取決於policy status 在以下存儲過程有這麽一句話,中了條件才會是Y sp_aes_tiu_pobas IF ((a_pol_sta="51" OR a_pol_sta="60" OR a_pol_sta="61") -- 008 end AND a_prod_cd in (select prod_cd from prod_mast where no_live="S")) THEN LET s_revival_redat="Y"; 爲了驗證中了Y的情況,找了一個保單號狀態為61的 select * from pol_basic where pol_sta = '61' 000000925970 select * from pol_person_hdr where pol_no='000000925970' agent code 00010002 再用這個賬號進去 utestaa01 Pass!23456 根據上面的信息輸入進去后發現頁面確實顯示了revival(請refer to 測試報告截圖) 之後Alex讓我通知user,就說這個是根據保單狀態動態顯示的. 总结： 就是和Prod code 没关系， 只和status 和保单其它数据有关系。 不用修改。 | re-test ok | assigned back to user | 2023-04-12 | 2023-04-14 | 2023-04-18 | 2023-04-18 |  | 2023-05-04 | 2023-05-15 | 2023-05-16
20230518 | AES | 826 | https://jira.pruconnect.net/projects/PHKLAES/issues/PHKLAES-826?filter=myopenissues | PIC-BCIM3- AES enquiry page | Simon Liao | AES | N/A | N/A | 不用改的原因是因为下拉框是从prulife同步过来的 就这张表select * from prulife@prulifeu1t:prod_mast | ready | assigned back to user | 2023-04-12 | 2023-04-14 | 2023-04-14 | 2023-04-14 |  | 2023-05-04 | 2023-05-15 | 2023-05-16 | refer to JIRA791
20230518 | AES | 827 | https://jira.pruconnect.net/projects/PHKLAES/issues/PHKLAES-827?filter=myopenissues | PIC-BCIM3 - AES Basic Info page | Vito Yu | AES | N/A | N/A | JIRA要求1： 不用改， 因为policy_details.jsp 里面 line 2123 benefitInfo 这个table， 下面的remark， 没有CIM2 的参考，remark来源于table JIRA要求2: benefit option， 没有prod code的条件需要加 | ready | assigned back to user | 2023-04-12 | 2023-04-14 | 2023-04-13 | 2023-04-13 |  | 2023-05-04 | 2023-05-15 | 2023-05-16 | need notify prulife to update correct name
20230518 | AES | 828 | https://jira.pruconnect.net/projects/PHKLAES/issues/PHKLAES-828?filter=myopenissues | PIC-BCIM3- Financial Overview | Heaton Liu | AES | 221201000-10 | ARMLET-IFX/221201000-10.sh created store/221201000-10.lst created store/221201000-10.sql created | Attention: missing store/sp_aes_benf_desc.sql see JIRA917 add sql insert aes_tbl_config 'BCIM3' 'BCIM3H' 'BCIM3M' 'BCIM3HM', for UI webpage searching and display | re-test ok | assigned back to user | 2023-04-12 | 2023-04-14 | 2023-04-13 | 2023-04-13 |  | 2023-05-04 | 2023-05-15 | 2023-05-16 | BCIM3' follow 'CIM2'
20230518 | AES | 828 | https://jira.pruconnect.net/projects/PHKLAES/issues/PHKLAES-828?filter=myopenissues | PIC-BCIM3- Financial Overview | Heaton Liu | SAES | 221201000-10 | WebContent/WEB-INF/view/proposal_policy/policy_details.jsp changed | add all product codes, so as to display remarks | re-test ok | assigned back to user | 2023-04-12 | 2023-04-14 | 2023-04-13 | 2023-04-13 |  | 2023-05-04 | 2023-05-15 | 2023-05-16 | BCIM3' follow 'CIM2'
20230518 | AES | 828 | https://jira.pruconnect.net/projects/PHKLAES/issues/PHKLAES-828?filter=myopenissues | PIC-BCIM3- Financial Overview | Heaton Liu | AESSVC | 221201000-10 | src/com/pru/hk/policy/life/dao/impl/LifePolicyDaoInformixImpl.java changd src/com/pru/hk/policy/life/spring/bean/LifePolicyBusinessBean.java changed | first java is for "TerminalBonusFaceValue displa", the 2nd java is for "已付讫的赔偿总额", 这个数据从SP 来 | re-test ok | assigned back to user | 2023-04-12 | 2023-04-14 | 2023-04-13 | 2023-04-13 |  | 2023-05-04 | 2023-05-15 | 2023-05-16 | BCIM3' follow 'CIM2'
20230518 | AES | 829 | https://jira.pruconnect.net/projects/PHKLAES/issues/PHKLAES-829?filter=myopenissues | PIC-BCIM3- AES Alteration Quotation | Heaton Liu | AES | N/A | N/A | 829 ---没任何代码或sql的修改。 https://jira.pruconnect.net/browse/PHKLAES-829 BCIM3 Alteration Quotation: From JIRA On AES > Alteration Quotation screen, should proceed the Alternation Quotation as the followings: Quotation type Description Plan [BCIM3] DECSUM Decrease Sum Assured allow INCSUM Increase Sum Assured Not Allowed (unless during Cooling-off period) CHMODE Mode Change allow ADDRID Add Rider allow REVIVAL Revival allow x REDATE Revival by re-dating Not allow 824 ---没任何代码或sql的修改。 From JIRA https://jira.pruconnect.net/browse/PHKLAES-824 CIM3 Quotation type Description Plan [CIM3] DECSUM Decrease Sum Assured allow INCSUM Increase Sum Assured Not Allowed (unless during Cooling-off period CHMODE Mode Change allow ADDRID Add Rider allow REVIVAL Revival allow x REDATE Revival by re-dating Not allow 824和829 一樣 ----------------- 1 下拉框call 了這個sp policy = PolicyDBHelper.getQuotationTypes(context, policy, pol_no);//下面sp是QuotationTypes.jsp下拉框數據源頭 call sp_aes_quot_types(?)//入參polNo 回來的Y就會顯示,其中REVIVAL是N,但是我們需要Y 問了alex 調查后,他說是因爲這個存儲過程sp_aes_tiu_pobas 裏面有個policy status判斷REVIVAL,如下: 2 其中REVIVAL這個值取決於policy status 在以下存儲過程有這麽一句話,中了條件才會是Y sp_aes_tiu_pobas IF ((a_pol_sta="51" OR a_pol_sta="60" OR a_pol_sta="61") -- 008 end AND a_prod_cd in (select prod_cd from prod_mast where no_live="S")) THEN LET s_revival_redat="Y"; 爲了驗證中了Y的情況,找了一個保單號狀態為61的 select * from pol_basic where pol_sta = '61' 000000925970 select * from pol_person_hdr where pol_no='000000925970' agent code 00010002 再用這個賬號進去 utestaa01 Pass!23456 根據上面的信息輸入進去后發現頁面確實顯示了revival(請refer to 測試報告截圖) 之後Alex讓我通知user,就說這個是根據保單狀態動態顯示的. 总结： 就是和Prod code 没关系， 只和status 和保单其它数据有关系。 不用修改。 | re-test ok | assigned back to user | 2023-04-12 | 2023-04-14 | 2023-04-18 | 2023-04-18 |  | 2023-05-04 | 2023-05-15 | 2023-05-16
20230518 | MYPRU | 1196 | https://jira.pruconnect.net/browse/PHKLMYPRUDENTIAL-1196 | [PPP221201000] PIC New Product – CIM3/BCIM3 | Vito Yu | AES | 221201000-10 | 221201000-20.sql created 221201000-10.lst changed | 这个sql是为了显示饼图: insert new record for 'CIM3','CIM3H','BCIM3','BCIM3H' | ready | assigned back to user | 2023-04-20 | 2023-04-28 | 2023-04-26 | 2023-04-26 |  | 2023-05-04 | 2023-05-15 | 2023-05-16
20230518 | MYPRU | 1196 | https://jira.pruconnect.net/browse/PHKLMYPRUDENTIAL-1196 | [PPP221201000] PIC New Product – CIM3/BCIM3 | Simon Liao | SESV | 221201000-10 | WebContent/WEB-INF/view/mypru/policy/detail/my_coverage.jspchanged WebContent/WEB-INF/view/mypru/policy/detail/policy_basic.jsp changed WebContent/WEB-INF/view/mypru/policy/financialSection/loanSection/loan_section_master.jsp changed WebContent/WEB-INF/view/mypru/policy/financialSection/basic_value.jsp changed | add CIM3 BCIM3 | ready | assigned back to user | 2023-04-20 | 2023-04-28 | 2023-04-26 | 2023-04-26 |  | 2023-05-04 | 2023-05-15 | 2023-05-16
20230518 | MYPRU | 1354 | https://jira.pruconnect.net/browse/PHKLMYPRUDENTIAL-1354 | BCIM3/BCIM3H - remove the remark for sum assured Bug of JIRA1196 | Simon Liao | N/A | N/A | only delete it in UAT: select * from benf_ctl where benf_cd in ('CIM3','CIM3H','BCIM3','BCIM3H') and ctl_type = 'SA_RMK' delete benf_ctl where benf_cd in ('CIM3','CIM3H','BCIM3','BCIM3H') and ctl_type = 'SA_RMK' | Twiny said actually CIM3/CIM3H also doesn't have this remark, don't know why BCIM3/BCIM3H shows this remark suddenly we found the dirty data in uat includes BCIM3, because remark comes from: select * from benf_ctl where benf_cd = 'CIE3' and ctl_type = 'SA_RMK' there is no record there so now sum assured can not see ^, now delete it it is ok, no need Add sql | ready | assigned back to user | 2023-04-20 | 2023-04-28 | 2023-04-26 | 2023-04-26 |  | 2023-05-04 | 2023-05-15 | 2023-05-16
20230518 | MYPRU | 1346 | https://jira.pruconnect.net/projects/PHKLMYPRUDENTIAL/issues/PHKLMYPRUDENTIAL-1346?filter=allopenissues | Treatment Sure - CIM3/BCIM3 https://jira.pruconnect.net/browse/PHKLVFPREV-43 | Heaton Liu | AES | 221201000-10 | ARMLET-IFX/221201000-10.sh created store/221201000-10.lst created store/221201000-10.sql created store/sp_cep_get_med_pol_dtl.sql changed | JIRA1346 and JIRA910 is for MYPRU and AES get data from store/sp_cep_get_med_pol_dtl.sql AES是手工输入网址 https://aesuat9.prudential.com.hk/saes/cepPolicyEnquiry/ | ready | assigned back to user | 2023-04-26 | 2023-04-28 | 2023-04-26 | 2023-04-28 |  | 2023-05-04 | 2023-05-15 | 2023-05-16
20230518 | AES | 910 | https://jira.pruconnect.net/browse/PHKLAES-910 | Treatment Sure - CIM3/BCIM3 | Heaton Liu | AES | 221201000-10 | ARMLET- store/221201000-10.lst created store/sp_cep_get_med_pol_dtl.sql changed |  | ready | assigned back to user | 2023-04-26 | 2023-04-28 | 2023-04-26 | 2023-04-28 |  | 2023-05-04 | 2023-05-15 | 2023-05-16
20230518 | AES | 910 | https://jira.pruconnect.net/browse/PHKLAES-910 | Treatment Sure - CIM3/BCIM3 | Vito Yu | AES | 221201000-10 | ARMLET- store/221201000-10.lst created store/sp_cep_get_med_pol_dtl.sql changed |  | ready | assigned back to user | 2023-04-26 | 2023-04-28 | 2023-04-26 | 2023-04-28 |  | 2023-05-04 | 2023-05-15 | 2023-05-16
20230518 | AES | 910 | https://jira.pruconnect.net/browse/PHKLAES-910 | Treatment Sure - CIM3/BCIM3 | Simon Liao | SAES | 221201000-10 | WebContent/WEB-INF/view/CEPPolicy/cep_enquiry.jsp | 测试的时候，也是手工输入 https://aesuat9.prudential.com.hk/saes/cepPolicyEnquiry/ 修改地方： 多添加一个'/' change <form id="frmSearchPolicy" name="frmSearchPolicy" action="/saes/cepPolicyEnquiry" method="POST" > to <form id="frmSearchPolicy" name="frmSearchPolicy" action="/saes/cepPolicyEnquiry/" method="POST" > | ready | assigned back to user | 2023-04-26 | 2023-04-28 | 2023-04-26 | 2023-04-28 |  | 2023-05-04 | 2023-05-15 | 2023-05-16
20230508 | AES | 914 | https://jira.pruconnect.net/browse/PHKLAES-914 | Hide Prepayment option in AES temporary | Vito Yu | SAES | 220700600_PM_EGIP | policy_details.jsp | remove prepayment option and remark 有趣的一个，如果 <p class="remark" align="left">^<spring:message code="pru.aes.title.premiumPrepaymentOptionRemark"/></p> 直接加 <!-- -->竟然无效，需要整行删除才行 | ready | assigned back to user | 2023-05-04 | 2023-05-04 | 2023-05-04 | 2023-05-04 |  | 2023-05-05 | 2023-05-05 | 2023-05-05
20230518 | MYPRU | 1344 | https://jira.pruconnect.net/projects/PHKLMYPRUDENTIAL/issues/PHKLMYPRUDENTIAL-1344?filter=allopenissues | [myPrudential] Add new letter for EGC disqualify premium prepayment offer | Heaton Liu | AESSVC | 220201900 | src/com/pru/hk/client/eai/dao/impl/EstatementEaiDaoImpl.java | 1344 branch 220201900 aessvc src/com/pru/hk/client/eai/dao/impl/EstatementEaiDaoImpl.java --------------------------- Twiny provided l09305283 abdc1234 l09302476 abdc1234 l09299749 abdc1234 sesv WebContent/WEB-INF/view/mypru/estatement/view.jsp EstatementController EstatementViewResult result = estatementFacade.viewEstatement(clientNum, role, policyNo, policyTime, policyType, aessvc EstatementBusinessBean @Transactional(rollbackFor = Exception.class) public EstatementViewResult viewEstatement(String clientCd, String role, String policyNo, String policyTime, String policyType, String language, Integer cPage, String sortField, String sortMode) throws BusinessException { //這個方法裏面,會去call EAI,把EAI的東西跟裏面的一個SP進行匹配,如果中的話,會把數據傳送到view,就是傳到給JSP上. trueList.addAll(getSubscribedStatement(policyType, polStr, strFrom, strTo, language, policyList, sortField, sortMode, clientCd)); user說沒有document顯示,是因爲eai回來沒數據,error code是000001,這是代表沒有doc. 如果回來是有數據的id,跟這個sp execute procedure SP_ESERV_SELECT_DOC_READ('07835844','LETT') 進行id匹配,中的話JSP就有數據了 這裏要注意是這裏for循環去call EAI, for (String type : typeList) { List<SubscribedStatement> tmpAvaList = new ArrayList<SubscribedStatement>(); tmpAvaList = estatementDaoEai.getAvailableStatement(polStr, type, strFrom, strTo); tmpAvaList = mapStatementName(tmpAvaList, policyList, policyType, language); availableList.addAll(tmpAvaList); } call完之後在setting object之前有個條件判斷, 把EAI回來的ReportType放進LETTER_LIST,改完這裏就完成了. if(LETTER_LIST.contains(rs.getString("ReportType").trim()) && ! policyDetail.getPolicy().getHkContractHeader().getPoliceStateCd().contains("OUTFORCE")){ ss.setTrueType(policyType); if(PRUConstant.ESTATEMENT_POLICY_TYPE_LETTER.equals(policyType)) { ss.setStatementType(rs.getString("doc_type_code").trim()); ss.setDocID(rs.getString("docid").trim()); ss.setPolicyNo(rs.getString("pol_no").trim()); ss.setStatementName(rs.getString("ReportType").trim()); ss.setDocumentName(rs.getString("ReportType").trim()); } else { ss.setStatementType(rs.getString(1).trim()); ss.setDocID(rs.getString(2).trim()); ss.setPolicyNo(rs.getString(4).trim()); ss.setStatementName(policyType); ss.setDocumentName(policyType); } ss.setIsImportant(rs.getString("HasAnnotation")); //logger.info("profiler===policyNo: " + ss.getPolicyNo()); //logger.info("profiler===DocumentName: " + ss.getDocumentName()); String displayName = policyDetail.getPolicy().getLifeAssuredClient().getFullName(); if (StringUtils.isNotEmpty(policyDetail.getPolicy().getLifeAssuredClient().getSecondaryFullName())) { displayName += " " + policyDetail.getPolicy().getLifeAssuredClient().getSecondaryFullName(); logger.debug("displayName:"+displayName); } ss.setLifeAssured(displayName); //logger.info("final displayName:"+displayName); } //ReportType 加進來,核心邏輯在這裏 private static final ArrayList<String> LETTER_LIST = new ArrayList<String>( Arrays.asList("CLIENT ADDRESS CHANGE LETTER (MULTIPLE POLICIES)", "CLIENT ADDRESS CHANGE - 1 SET (MULTIPLE POLICIES)", "CLIENT ADDRESS CHANGE LETTER (SINGLE POLICIES)", "CLIENT ADDRESS CHANGE - 1 SET (SINGLE POLICY)", "FINANCIAL MOVEMENT CONFIRMATION LETTER", "SERVICE REQUEST CONFIRMATION", "CHANGE OF ADDRESS REJECT LETTER", "CHANGE OF PAYOUT OPTION CONFIRMATION LETTER", "POLICY CHANGE - REJECT LETTER", "CONFIRMATION LETTER FOR DECLINING BPO (MOVEMENT)", "FUND TRADING LETTER", "DIVIDEND REINVESTMENT LETTER", "CONFIRMATION - UPDATE OF CHINESE NAME", "SETUP DDA/CCDDA REJECT LETTER", "REJECT LETTER", "AUTOPAY COLLECTION REJECT LETTER", "MAJOR - REJECT LETTER", "CHANGE OF BENEFICIARY", "RETIREMENT INCOME OPTION NOTICE", "MATURITY NOTICE", "INSUFFICIENT ACCUMULATED VALUE REMINDER", "LOAN REPAYMENT REMINDER", "MATURITY NOTICE (UL)", "CIES LETTER - FI APPOINTMENT TERMINATION NOTICE", "MATURITY REMINDER NOTICE", "AUTOMATIC PREMIUM LOAN NOTICE (FOR OWNER)", "INSUFFICIENT FUND BALANCE REMINDER", "INSUFFICIENT FUND BALANCE REMINDER (SWB)", "CESSATION OF PREMIUM HOLIDAY (FOR OWNER)", "TERMINATION NOTICE OF SUPPLEMENTARY BENEFIT", "LAPSE/RPU NOTICE (FOR OWNER)", "LAPSE NOTICE (PRUUNIVERSAL LIFE) (FOR OWNER)", "LAPSE NOTICE (FOR OWNER)", "PREMIUM HOLIDAY NOTICE (FOR OWNER)", "CFI CONSERVATION LETTER (FOR PDD -D0675 CASE)", "CLOSURE OF FUND ACCOUNT (CLOSE A/C BY USER)", "MATURITY PAYMENT INSTRUCTIONS CONFIRMATION", "MATURITY PAYMENT ADVICE", "CHANGE OF DEATH BENEFIT OPTION / MONTHLY INCOME PAYMENT METHOD", "UNSUCCESSFUL MONTHLY INCOME PAYMENT BY DIRECT DEPOSIT", "PAYMENT LETTER (FOR CASE CHEQUE DESTINATION = AGT)", "PENDING LETTER", "REVIVAL LETTER", "REVIVAL LETTER (PRUUNIVERSAL LIFE)", "REVIVAL LETTER-FOR TRADITIONAL POLICY WITH INVP", "TERMINATION CONFIRMATION LETTER", "CLOSURE OF FUND ACCOUNT", "CFI CONSERVATION LETTER (FOR AGENCY AND BROKER)", "NO CLAIM BONUS CUSTOMER LETTER", "NOTIFICATION FOR RELEASE OF MONTHLY INCOME PAYMENT BY CHEQUE", "CHANGE SMOKING HABIT LETTER (WITH CV REFUND)", "INCOMPLETE APPLICATION", "CONFIRMATION OF POLICY LOAN REPAYMENT", "CONFIRMATION OF POLICY TERMINATION (PLAN CHANGE)", "CONFIRMATION OF APPLICATION WITHDRAWAL", "CHANGE OF OCCUPATION/AVOCATION/SMOKING HABIT (ADJUSTMENT)", "CHANGE OF OCCUPATION/AVOCATION/SMOKING HABIT", "NOTIFICATION OF BOUNCED CHEQUE", "SUPPLEMENTARY INFORMATION", "SURRENDER CONSERVATION LETTER", "TERMINATION CONSERVATION LETTER", "CONFIRMATION OF POLICY TERMINATION", "CONFIRMATION LETTER FOR DECLINING BPO (PAYMENT)", "PAYMENT LETTER FOR ANNIVERSARY PAYMENT - CHI", "MAJOR- SUSPENSION ON SELL RIDERS BY SPECIFIC AGENT", "PAYMENT LETTER FOR ANNIVERSARY PAYMENT", "FOLLOW-UP LETTER FOR OUTDATED CHEQUE", "IFS-MP COVER LETTER", "AUTOPAY COLLECTION REJECT LETTER - EXCEED LIMIT", "PAYMENT OPTION NOTIFICATION LETTER - DOUBLE TREASURE", "HAVE NOT RECEIVED UPDATED BANK ACCOUNT INFORMATION", "CHANGE OF ABSOLUTE ASSIGNMENT", "CHANGE OF ABSOLUTE ASSIGNMENT (MONTHLY INCOME PLAN)", "CHANGE OF COLLATERAL ASSIGNMENT", "CHANGE OF COLLATERAL ASSIGNMENT (MONTHLY INCOME PLAN)", "CHANGE OF OWNERSHIP FOR JUVENILE POLICY", "CHANGE OF PERSONAL PARTICULARS (MULTI)", "CHANGE OF PERSONAL PARTICULARS (SINGLE)", "CHANGE OF SIGNATURE", "CHANGE OF TRUSTEE", "CIES LETTER - COPY OF FI AGREEMENT (FOR HKID/3RD FI)", "CIES LETTER - COPY OF FI AGREEMENT (FOR OWNER)", "CIES LETTER - FUND VALUE LETTER", "CIES LETTER - POLICY UPDATE (FOR HKID/3RD FI)", "CIES LETTER - POLICY UPDATE (FOR OWNER)", "CIES LETTER - UPDATE ON APPOINTED FI CIES APPLICATION STATUS (FOR HKID/3RD FI)", "CIES LETTER - UPDATE ON APPOINTED FI CIES APPLICATION STATUS (FOR OWNER)", "CLIENT DATA - OWNERSHIP OF POLICY (MONTHLY INCOME PLAN)", "CLIENT NOTIFICATION FOR HTPR CONVERSION", "CONFIRMATION OF REVOKING EXISTING CONTINGENT OWNER", "FATCA LETTER", "LSAP LETTER (PRUUNIVERSAL LIFE SERIES) (FOR OWNER)", "PREMIUM HOLIDAY CONSERVATION LETTER (AGENCY)", "PREMIUM HOLIDAY CONSERVATION LETTER (PDD)", "RELEASE OF COLLATERAL ASSIGNMENT", "TERM CONVERSION CONFIRMATION LETTER PRINTING (LETTER)", "TRANSFER OF OWNERSHIP CONFIRMATION LETTER", "TRANSFER OF OWNERSHIP CONFIRMATION LETTER (MONTHLY INCOME PLAN)", "CRS LETTER FOR INDIVIDUAL (CIC)", "CRS LETTER FOR ENTITY (CIC)", "PROOF OF LEVY", "CHI", //CHICOL "IMN", // IMNCOF IMNOPT ? IMNCFF "QDAP TAX LETTER", // PRDA Tax Letter "REGULAR WITHDRAWAL CONFIRMATION LETTER", // "REGULAR WITHDRAWAL CANCELLATION LETTER", // "GRACE PERIOD EXTENSION (90 DAYS) CONFIRMATION LETTER", //Special Unemployment Letter "FREE UNEMPLOYMENT BENEFIT (180 DAYS) CONFIRMATION LETTER", //Special Unemployment Letter, "VHIS TAX REFUND LETTER", // PRDA Revamp (PRDA10 & PRDA20) PHKLMYPRUDENTIAL-283, "PREMIUM FINAL REMINDER LETTER (61 DAY)", //PHKLNFO90-13 "CUSTOMER LETTER OF PREMIUM DISCOUNT OR REFUND", // Customer Letter PMAP00197 "FINAL POLICY RENEWAL PREMIUM REMINDER", //PPP200603800 - PHKLNFO90-13 "PR COVERING LETTER", //GL27 PHKLSUPPRESSHARDCOPY-8 (TBC) => CONFIRMATION OF POLICY REPLACEMENT FORM(S) "POLICY REPLACEMENT FOLLOW UP LETTER", //GL27 "POLICY REPLACEMENT FOLLOW UP REMINDER LETTER", //GL27 "POLICY LOAN DETAIL ENQUIRY", "CANCELLATION FOR DESIGNATED PERSON LETTER", //PHKLSUPPRESSHARDCOPY-8 "CONFIRMATION OF POLICY REPLACEMENT FORM(S)", //PHKLSUPPRESSHARDCOPY-8 "CREDITING INTEREST RATE UPDATE LETTER", //PHKLULCIRCHGOCT22-5 "CHANGE OF DEATH BENEFIT OPTION /MONTHLY INCOME PAYMENT METHOD", //PHKLEGI-111 "SCB PREMIUM FINANCING - ACKNOWLEDGEMENT OF NOTICE OF ASSIGNMENT (BENEFICIARY)", //PHKLEGI-122 "DELIGHTFUL REWARDS DISTRIBUTION NOTICE", //PHKLBD20083-19 "LETTER OF DISQUALIFY PREMIUM PREPAYMENT" //PHKLMYPRUDENTIAL-1344 ) ); | ready | assigned back to user | 2023-05-04 | 2023-05-05 | 2023-05-04 | 2023-05-04 |  | 2023-05-08 | 2023-05-15 | 2023-05-16
20230518 | AES | 913 | https://jira.pruconnect.net/browse/PHKLAES-913 | AES - PIC Day 2 - update existing form name | Simon Liao | AES | 221201000-10 | 221201000-10.sql created | updated form name for " PMAP000211" | ready | assigned back to user | 2023-05-04 | 2023-05-04 | 2023-04-28 | 2023-04-28 |  | 2023-05-08 | 2023-05-15 | 2023-05-16
20230518 | AES | 919 | https://jira.pruconnect.net/browse/PHKLAES-919 | https://jira.pruconnect.net/browse/PHKLAES-919 | Simon Liao | AES | 221201000-10 | 221201000-30.sql changed | add missing form id in table wf_misc_code_tbl | ready | assigned back to user | 2023-05-12 | 2023-05-12 | 2023-05-12 | 2023-05-12 |  | 2023-05-12 | 2023-05-12 | 2023-05-16
20230518 | AES | 917 | https://jira.pruconnect.net/browse/PHKLAES-917 | AES Financial overview - Total Claim Paid - missing field name, missing remarks and incorrect value | Heaton Liu | AES | 221201000-10 | store/sp_aes_benf_desc.sql | This is a defeat of JIRA823 | ready | assigned back to user | 2023-05-04 | 2023-05-05 | 2023-05-04 |  |  |  | 2023-05-15 | 2023-05-16
20230518 | AES | 917 | https://jira.pruconnect.net/browse/PHKLAES-917 | AES Financial overview - Total Claim Paid - missing field name, missing remarks and incorrect value | Heaton Liu | SAES | 221201000-10 | /WEB-INF/view/proposal_policy/policy_details.jsp | This is a defact of JIRA823 | ready | assigned back to user | 2023-05-04 | 2023-05-05 | 2023-05-04 |  |  |  | 2023-05-15 | 2023-05-16
20230518 | AES | 917 | https://jira.pruconnect.net/browse/PHKLAES-917 | AES Financial overview - Total Claim Paid - missing field name, missing remarks and incorrect value | Heaton Liu | AESSVC | 221201000-10 | src/com/pru/hk/policy/life/dao/impl/LifePolicyDaoInformixImpl.java changd src/com/pru/hk/policy/life/spring/bean/LifePolicyBusinessBean.java changed | This is a defact of JIRA823 first java is for "TerminalBonusFaceValue displa", the 2nd java is for "已付讫的赔偿总额", 这个数据从SP 来 | ready | assigned back to user | 2023-05-04 | 2023-05-05 | 2023-05-04 |  |  |  | 2023-05-15 | 2023-05-16
20230518 | AES | 825 | https://jira.pruconnect.net/browse/PHKLAES-825 | PIC-CIM3/BCIM3-add form code in AES- Submitted Documents and Images | Simon Liao | AES | 221201000-10 | 221201000-30.sql changed | add all related forms |  | assigned back to user | 2023-05-04 | 2023-05-04 | 2023-05-04 | 2023-05-04 |  | 2023-05-04 | 2023-05-15 | 2023-05-16
20230602 | MYPRU | 1358 | https://jira.pruconnect.net/browse/PHKLMYPRUDENTIAL-1358 | "221201301" Update ALA, AJE, AJS and ASE fund name and remark | Simon Liao | SESV | 221201301-20 | WebContent/WEB-INF/message/mypru/view_en.properties changed WebContent/WEB-INF/message/mypru/view_zh.properties changed WebContent/WEB-INF/view/main/fund_select_overlay.jsp changed WebContent/WEB-INF/view/main/fund_select_overlay_remark.jsp changed | add 'ALA' 'AJE' 'AJS' 'ASE' fund name in jsp | ready | assigned back to user | 2023-05-29 | 2023-05-29 | 2023-05-29 | 2023-05-29 | 2023-05-29 | 2023-05-30 | 2023-05-29 | 2023-06-02
20230608 | MYPRU | 1373 | https://jira.pruconnect.net/browse/PHKLMYPRUDENTIAL-1373 | IN02370957 myPrudential production issue - cannot select FEA fund | Simon Liao | J:\IT\ES1\Share\20230608 release J:\IT\ES1\Share\BPM Solution\PA\ePA-2019\Releases\20230608 | project code:IN02370957 |  | 缺implementation notice | https://collaborate.pruconnect.net/display/PHKLMYPRU/IN02370957+myPrudential+production+issue+-+cannot+select+FEA+fund | 100% deployment progress | 2023-06-08 | 2023-06-08 | 2023-06-08 | 2023-06-08 | 2023-06-08
20230619 | AES | 835 | https://jira.pruconnect.net/projects/PHKLAES/issues/PHKLAES-835?filter=myopenissues | PIC-P3S - AES enquiry page | Simon Liao | AES | N/A | N/A |  | ready | uat-signed-off | 2023-04-14 | 2023-04-21 | 2023-04-14 | 2023-04-14 | 2023-06-05 | 2023-06-06 | 06/13/2023 | 2023-06-19
20230619 | AES | 836 | https://jira.pruconnect.net/projects/PHKLAES/issues/PHKLAES-836?filter=myopenissues | PIC-P3S - AES Basic Info page | Simon Liao | SAES | 220201000 | WebContent/WEB-INF/view/proposal_policy/policy_details.jsp changed | remove " Prepaid Discount Promotion" in policy detail for product code 'P3S' | ready | uat-signed-off | 2023-04-26 | 2023-04-28 | 2023-04-26 | 2023-04-26 | 2023-06-05 | 2023-06-06 | 06/13/2023 | 2023-06-19
20230619 | AES | 836 | https://jira.pruconnect.net/projects/PHKLAES/issues/PHKLAES-836?filter=myopenissues | PIC-P3S - AES Basic Info page | Vito Yu | SAES | 220201000 | WebContent/WEB-INF/message/aes/locale_en.properties changed WebContent/WEB-INF/message/aes/locale_zh.properties changed WebContent/WEB-INF/view/proposal_policy/policy_details.jsp changed | add 'P3S' to display benefit in policy detail webpage | ready | uat-signed-off | 2023-04-14 | 2023-04-21 | 2023-04-21 | 2023-04-21 | 2023-06-05 | 2023-06-06 | 06/13/2023 | 2023-06-19
20230619 | AES | 836 | https://jira.pruconnect.net/projects/PHKLAES/issues/PHKLAES-836?filter=myopenissues | PIC-P3S - AES Basic Info page | Vito Yu | AESSVC | 220201000 | src/com/pru/hk/policy/life/dao/impl/LifePolicyDaoInformixImpl.java | add "P3S" in array list | ready | uat-signed-off | 2023-04-14 | 2023-04-21 | 2023-04-21 | 2023-04-21 | 2023-06-05 | 2023-06-06 | 06/13/2023 | 2023-06-19
20230619 | AES | 837 | https://jira.pruconnect.net/projects/PHKLAES/issues/PHKLAES-837?filter=myopenissues | PIC-P3S- Financial Overview | Heaton Liu | AES | 220201000 | store/220201000.sql created store/220201000.lst created ARMLET-IFX/220201000.sh created | add sql insert aes_tbl_config 'P3S' | ready | uat-signed-off | 2023-04-14 | 2023-04-21 | 2023-04-18 | 2023-04-18 | 2023-06-05 | 2023-06-06 | 06/13/2023 | 2023-06-19
20230619 | AES | 837 | https://jira.pruconnect.net/projects/PHKLAES/issues/PHKLAES-837?filter=myopenissues | PIC-P3S- Financial Overview | Heaton Liu | AESSVC | 220201000 |  | add condition 'P3S' | ready | uat-signed-off | 2023-04-14 | 2023-04-21 | 2023-04-18 | 2023-04-18 | 2023-06-05 | 2023-06-06 | 06/13/2023 | 2023-06-19
20230619 | AES | 838 | https://jira.pruconnect.net/projects/PHKLAES/issues/PHKLAES-838?filter=myopenissues | PIC-P3S- AES Alteration Quotation | Heaton Liu | AES | N/A | N/A | N/A | ready | uat-signed-off | 2023-04-14 | 2023-04-21 | 2023-04-19 | 2023-04-19 | 2023-06-05 | 2023-06-06 | 06/13/2023 | 2023-06-19
20230619 | AES | 839 | https://jira.pruconnect.net/projects/PHKLAES/issues/PHKLAES-839?filter=myopenissues | PIC-P3S-add form code in AES- Submitted Documents and Image | Simon Liao | AES | N/A | N/A | No new form id | N/A | uat-signed-off | 2023-04-14 | 2023-04-21 | 2023-04-19 | 2023-04-19 | 2023-06-05 | 2023-06-06 | 06/13/2023 | 2023-06-19 | Ricky said so far no form code
20230619 | MYPRU | 1143 | https://jira.pruconnect.net/browse/PHKLMYPRUDENTIAL-1143 | SCB Omni New Product – P3S https://jira.pruconnect.net/browse/PHKLSCBDIY-116 [P3S] [myPrudential] Display Policy Details | Vito Yu | AESSVC | 220201000 | AESSVC: src/com/pru/hk/to/policy/life/LifePolicyTO.java src/com/pru/hk/policy/life/spring/bean/LifePolicyBusinessBean.java | first of all: 1. add all P3S according to P8S, policy_basic.jsp, my_coverage.jsp, (policy_summary.jsp financial_summary.jsp--不用修改了) 2. insert into prod_grp_efolder_dtl(prod_grp_id,prod_cd,last_upd_dt,last_upd_usr) values(1,'P3S',current,'220201000'); a) Landing page -> My Policies In the pie chart, add P3S to "Savings & Protection " Inforce policies count. ---如果上面都改好了， 这里就直接有了 b) On Policy Details, hide Death Benefit Settlement Option--- policy_basic.java <c:if test="${policyStatus >= 40 && policyStatus < 60}"> <c:if test="${ 'MIP' == productType.prodCd ¦¦ 'PLJ' == productType.prodCd ¦¦ 'P8S' == productType.prodCd ¦¦ 'P3S' == productType.prodCd ¦¦ ---Add this----但目前这个需求是要隐藏，所以需要删掉，就是说这里不需要加P3S c) On Policy Details > My Coverage, show the plan details of P3S policy: ---上面my_coverage.java就是这个remarks 金额加 货币代号 ---AESSVC SESV remark SESV: policy_basic.jsp changed my_coverage.jsp changed view_zh.properties changed view_en.properties changed AESSVC: src/com/pru/hk/to/policy/life/LifePolicyTO.java src/com/pru/hk/policy/life/spring/bean/LifePolicyBusinessBean.java | re-test | uat-signed-off | 2023-04-14 | 2023-04-21 | 2023-04-21 | 2023-04-21 | 2023-06-05 | 2023-06-06 | 06/13/2023 | 2023-06-19
20230619 | MYPRU | 1143 | https://jira.pruconnect.net/browse/PHKLMYPRUDENTIAL-1143 | [P3S] [myPrudential] Disable UPOP payment and MPGS payment https://jira.pruconnect.net/browse/PHKLSCBDIY-117 | Vito Yu | SESV | N/A | N/A | N/A | ready | uat-signed-off | 2023-04-14 | 2023-04-21 | 2023-04-20 | 2023-04-20 | 2023-06-05 | 2023-06-06 | 06/13/2023 | 2023-06-19
20230619 | MYPRU | 1143 | https://jira.pruconnect.net/browse/PHKLMYPRUDENTIAL-1143 | [P3S] [myPrudential] Disable Policy Future Value Illustration Report https://jira.pruconnect.net/browse/PHKLSCBDIY-118 | Heaton Liu | SESV | N/A | N/A | N/A | ready | uat-signed-off | 2023-04-14 | 2023-04-21 | 2023-04-20 | 2023-04-20 | 2023-06-05 | 2023-06-06 | 06/13/2023 | 2023-06-19
20230619 | PRUENROL | 36 | https://jira.pruconnect.net/browse/PHKLIMCS-36 | Support bilingual display in Online Enrollment | Yu Sheng Chen | PRUENROL | 230179100-02 | src/com/pru/hk/pruenrol/controller/BaseController.java WebContent/WEB-INF/message/locale_en.properties WebContent/WEB-INF/message/locale_zh.properties WebContent/WEB-INF/view/event/attendance_course.jsp WebContent/WEB-INF/view/event/attendance_event_info.jsp WebContent/WEB-INF/view/event/attendance_session.jsp WebContent/WEB-INF/view/event/attendance_subsession.jsp WebContent/WEB-INF/view/event/edit.jsp WebContent/WEB-INF/view/common_page_header.jsp | 修复中英文切换，中文状态下，显示的依然是英文的问题。 |  | waiting uat-signed-off | 2023-06-06 | 2023-08-06 | 2023-06-06 | 2023-06-07 | 2023-06-08 | 2023-06-08 | 2023-06-13 | 2023-06-19
20230619 | MYPRU | 1143 | https://jira.pruconnect.net/browse/PHKLMYPRUDENTIAL-1143 | SCB Omni New Product – P3S https://jira.pruconnect.net/browse/PHKLSCBDIY-116 | Vito Yu | SESV | 220201000 | policy_basic.jsp changed my_coverage.jsp changed view_zh.properties changed view_en.properties changed loan_section_template_a.jsp changed basic_value.jsp changed savingProtectionRevamp.jsp changed | first of all: 1. add all P3S according to P8S, policy_basic.jsp, my_coverage.jsp, (policy_summary.jsp financial_summary.jsp--不用修改了) 2. insert into prod_grp_efolder_dtl(prod_grp_id,prod_cd,last_upd_dt,last_upd_usr) values(1,'P3S',current,'220201000'); a) Landing page -> My Policies In the pie chart, add P3S to "Savings & Protection " Inforce policies count. ---如果上面都改好了， 这里就直接有了 b) On Policy Details, hide Death Benefit Settlement Option--- policy_basic.java <c:if test="${policyStatus >= 40 && policyStatus < 60}"> <c:if test="${ 'MIP' == productType.prodCd ¦¦ 'PLJ' == productType.prodCd ¦¦ 'P8S' == productType.prodCd ¦¦ 'P3S' == productType.prodCd ¦¦ ---Add this----但目前这个需求是要隐藏，所以需要删掉，就是说这里不需要加P3S c) On Policy Details > My Coverage, show the plan details of P3S policy: ---上面my_coverage.java就是这个remarks 金额加 货币代号 ---AESSVC SESV remark SESV: policy_basic.jsp changed my_coverage.jsp changed view_zh.properties changed view_en.properties changed savingProtectionRevamp.jsp---用于饼图 AESSVC: src/com/pru/hk/to/policy/life/LifePolicyTO.java src/com/pru/hk/policy/life/spring/bean/LifePolicyBusinessBean.java |  | uat-signed-off | 2023-04-14 | 2023-04-21 | 2023-04-21 | 2023-04-21 | 2023-06-05 | 2023-06-13 |  | 2023-06-19
20230619 | MYPRU | 1343 | https://jira.pruconnect.net/browse/PHKLMYPRUDENTIAL-1343 | EGC / EGCH / EGCR / EGCG / EGCA / EGCC FVI page | Simon Liao | SESV | 220201900 | 220201900.sql created pre-production.lst changed was9_common.lst changed | 在table fvi_template_config添加prod code | ready | uat-signed-off | 2023-05-19 | 2023-05-22 | 2023-05-19 | 2023-05-25 | 2023-06-05 | 2023-06-13 |  | 2023-06-19
20230619 | MYPRU | 1343 | https://jira.pruconnect.net/browse/PHKLMYPRUDENTIAL-1343 | EGC / EGCH / EGCR / EGCG / EGCA / EGCC FVI page | Simon Liao | SESV | 220201900 | WebContent/WEB-INF/message/fvi/locale_en.properties changed WebContent/WEB-INF/message/fvi/locale_zh.properties changed WebContent/WEB-INF/view/mypru/policy/fvi/template/wpp_22.jsp created | properties files add header01 header02 jsp file add new layout | ready | uat-signed-off | 2023-05-19 | 2023-05-22 | 2023-05-19 | 2023-05-25 | 2023-06-05 | 2023-06-13 |  | 2023-06-19
20230619 | AES | 930 | https://jira.pruconnect.net/browse/PHKLAES-930 | [PIC Day 1.1] EGC - AES Future Value Illustration (FVI) | Heaton Liu | SAES | 220201900 | WebContent/WEB-INF/message/fvi/locale_en.properties changed WebContent/WEB-INF/message/fvi/locale_zh.properties changed WebContent/WEB-INF/view/proposal_policy/fvi/template/wpp_22.jsp created | properties files add header01 header02 jsp file add new layout | ready | waiting uat-signed-off | 2023-05-30 | 2023-05-30 | 2023-05-30 | 2023-05-30 | 2023-06-05 | 2023-06-13 |  | 2023-06-19
20230619 | MYPRU | 1371 | https://jira.pruconnect.net/browse/PHKLMYPRUDENTIAL-1371 | https://jira.pruconnect.net/browse/PHKLEGI-208 Add a static remark for the applicable monthly income products under Monthly Income table | Yu Sheng Chen | SESV | PPP220401600-EGI | WebContent/WEB-INF/message/policydetail/view_en.properties changed WebContent/WEB-INF/message/policydetail/view_zh.properties changed WebContent/WEB-INF/view/mypru/policy/financialSection/monthlyIncomeSection/monthlyIncome_section_template_c.jsp changed WebContent/WEB-INF/view/mypru/policy/financialSection/monthlyIncomeSection/rip.jsp changed WebContent/WEB-INF/view/mypru/policy/financialSection/pmih.jsp changed WebContent/WEB-INF/view/mypru/policy/financialSection/prai.jsp changed | update comment, remove all condition for a static remark | Pending for prulife | waiting uat-signed-off | 2023-06-08 | 2023-06-12 | 2023-06-08 | 2023-06-09 | 2023-06-12 | 2023-06-13 |  | 2023-06-19
20230619 | AES | 938 | https://jira.pruconnect.net/browse/PHKLAES-938 | AES- removing prepayment flag symbol and remarks | Yu Sheng Chen | SAES | 220700600_PM_EGIP | WebContent/WEB-INF/view/proposal_policy/policy_details.jsp changed WebContent/WEB-INF/message/aes/locale_en.properties changed WebContent/WEB-INF/message/aes/locale_zh.properties changed | 1.删除备注：^只顯示於2013年6月21日或以後推出並設有預繳保費選項的產品 2.删除“預繳保費選項^”中的^符号。 | ready | waiting uat-signed-off | 2023-06-09 | 2023-06-13 | 2023-06-09 | 2023-06-12 | 2023-06-13 | 2023-06-13 | 2023-06-14 | 2023-06-19
20230619 | AES | 920 | https://jira.pruconnect.net/browse/PHKLAES-920 | Unhide Prepayment option in AES | Simon Liao | SAES | 220700600_PM_EGIP | policy_details.jsp | add prepayment option and remark | ready | assigned back to user | 2023-05-29 | 2023-05-29 | 2023-05-29 | 2023-05-29 | 2023-06-05 | 2023-06-06 | 2023-06-20 | 2023-06-21
20230630 | AES | 912 | https://jira.pruconnect.net/browse/PHKLAES-912 | Treatment Sure - VFP | Heaton Liu | AES | 221201100 | ARMLET-IFX/221201100.sh created store/221201100.lst created store/sp_cep_get_med_pol_dtl.sql changed store/sp_cep_get_med_pol.sqlMODIFIED | utestaa01 Pass!23456 網頁請求 https://aesuat9.prudential.com.hk/saes/cepPolicyEnquiry/ 入口 src/com/pru/hk/aes/controller/ceppolicy/CEPPolicyEnquiryController.java @Controller @RequestMapping(value = "/cepPolicyEnquiry") public class CEPPolicyEnquiryController extends BaseController{ //call aessvc 拿數據 List<CEPPolicy> cepPolicyList = cepPolicyFacade.getCEPPolicyList(fullname, dob, idNo); //get data from backend aessvc src/com/pru/hk/policy/life/ws/CEPPolicySoapService.java //到最裏面就是call了這個sp @Override public List<CEPPolicy> getCEPPolicyList(final String fullname, final Date dob, final String idNo) throws BusinessException { final long lStartTime = System.currentTimeMillis(); final String szLogPrefix = "[AESSVC][CEPPolicyDao][getCEPPolicyList] "; HibernateJdbcWorker<List<CEPPolicy>> hibernateJdbcWorker = new HibernateJdbcWorker<List<CEPPolicy>>( sessionFactory, null) { @Override public void performExecute(Connection conn, CallableStatement stmt, ResultSet rs) throws SQLException { String sql = "call sp_cep_get_med_pol(?,?,?,?,?,?,?,?,?)"; | ready | user sign off done | 2023-05-19 | 2023-05-22 | 2023-05-18 | 2023-05-19 | 2023-06-05 |  |  | 2023-06-27
20230630 | AES | 912 | https://jira.pruconnect.net/browse/PHKLAES-912 | Treatment Sure - VFP | Heaton Liu | SAES | 221201100 | WebContent/WEB-INF/view/CEPPolicy/cep_enquiry.jspMODIFIED | if product code: VFP, VFPP, VFPQ, VFPR, anniversary date (01/10/2023) >= 01/07/2023 and today date (02/10/2023) >= anniversary date (01/10/2023), the policy can be search; otherwise, the policy cannot be searched and with Reason: This policy is not yet renewed to new anniversary year, it is not eligible for the service | ready | user sign off done | 2023-05-19 | 2023-05-22 | 2023-05-18 | 2023-05-19 | 2023-06-05 |  |  | 2023-06-27
20230630 | MYPRU | 1350 | https://jira.pruconnect.net/browse/PHKLMYPRUDENTIAL-1350 | Treatment Sure - VFP | Heaton Liu | AES | 221201100 | ARMLET-IFX/221201100.sh created store/221201100.lst created store/sp_cep_get_med_pol_dtl.sql changed | 加了这个sp就可以看到保单详情链接 保单详情顶头上有个field是保单详情链接,点进去下pdf | ready | user sign off done | 2023-05-22 | 2023-05-24 | 2023-05-19 | 2023-05-19 | 2023-06-05 |  |  | 2023-06-27
20230630 | AES | 77 | https://jira.pruconnect.net/browse/PHKLVFPREV-77 | PIC - AES Treatment Sure and Green Channel for VFPR | Heaton Liu | SAES | 221201100 | WebContent/WEB-INF/view/CEPPolicy/cep_enquiry.jsp | 测试的时候，也是手工输入 https://aesuat9.prudential.com.hk/saes/cepPolicyEnquiry/ add remark | ready | user sign off done | 2023-05-29: 2023-06-08; 2023-05-29: 2023-06-08; 2023-05-29: 2023-06-08; 2023-05-29: 2023-06-08
20230630 | MYPRU | 1369 | https://jira.pruconnect.net/browse/PHKLMYPRUDENTIAL-1369 | "221201100" Follow VFP to display policy information for VFPP and VFPQ | Heaton Liu | SESV | 221201100 | WebContent/WEB-INF/view/mypru/policy/detail/anchor_tag.jspMODIFIED WebContent/WEB-INF/view/mypru/policy/detail/my_coverage.jspMODIFIED WebContent/WEB-INF/view/mypru/policy/detail/policy_basic.jspMODIFIED WebContent/WEB-INF/view/mypru/policy/financialSection/ncb_section.jspMODIFIED WebContent/WEB-INF/view/mypru/policy/financialSection/premium_deposit_account.jspMODIFIED WebContent/WEB-INF/view/mypru/policy/detail.jspMODIFIED WebContent/WEB-INF/view/mypru/policy/index.jspMODIFIED WebContent/WEB-INF/view/mypru/policy/medicalCriticalIllness.jspMODIFIED WebContent/WEB-INF/view/mypru/policy/medicalCriticalIllnessRevamp.jspMODIFIED | 用户说VFPP VFPQ 要follow VFP | ready | user sign off done | 2023-05-29: 2023-06-07; 2023-05-29: 2023-06-08; 2023-05-29: 2023-06-07; 2023-05-29: 2023-06-08
20230630 | MYPRU | 1369 | https://jira.pruconnect.net/browse/PHKLMYPRUDENTIAL-1369 | "221201100" Follow VFP to display policy information for VFPP and VFPQ | Heaton Liu | AESSVC | 221201100 | src/com/pru/hk/util/PRUConstant.javaMODIFIED | 用户说VFPP VFPQ 要follow VFP | ready | user sign off done | 2023-05-29: 2023-06-07; 2023-05-29: 2023-06-08; 2023-05-29: 2023-06-07; 2023-05-29: 2023-06-08
20230630 | MYPRU | 1369 | https://jira.pruconnect.net/browse/PHKLMYPRUDENTIAL-1369 | "221201100" Follow VFP to display policy information for VFPP and VFPQ | Heaton Liu | APPSVC | 221201100 | src/com/pru/hk/client/spring/bean/ClientEligibilityBusinessBean.javaMODIFIED | 用户说VFPP VFPQ 要follow VFP | ready | user sign off done | 2023-05-29: 2023-06-07; 2023-05-29: 2023-06-08; 2023-05-29: 2023-06-07; 2023-05-29: 2023-06-08
20230630 | AES | 939 | https://jira.pruconnect.net/browse/PHKLAES-939 | https://jira.pruconnect.net/browse/PHKLPROJM-1662 Project M - eReply - Update follow-up options for returned mail item | Simon Liao | SAES | 221201100 | view/ereply/ereply_searchresult_individual.jsp | 目前JIRA提到的2個差異畫面都調用這個JSP，因爲這個JSP的這段代碼有channel M 限定，注釋這個，然後把2段刪掉就可以了。 | ready | user sign off done | 2023-06-19 | 2023-06-19 | 2023-06-19 | 2023-06-19 | 2023-06-21 | 2023-06-26 | 2023-06-28 | 2023-07-01
20230706 | MYPRU | 1249 | https://jira.pruconnect.net/browse/PHKLMYPRUDENTIAL-1249 | [PPP220700800] PIC New Product – PVP (PWSP revamp)---JIRA1249-12 Show policy details | Heaton Liu | SESV | 220700800-10 | WebContent/WEB-INF/view/mypru/policy/financialSection/loanSection/loan_section_template_a.jspMODIFIED WebContent/WEB-INF/view/mypru/policy/financialSection/basic_value.jspMODIFIED esv_hk/store/informix/was9_common.lstMODIFIED esv_hk/store/informix/pre-production.lstMODIFIED esv_hk/store/informix/SP_ESERV_GET_PL_BENF_NAME.sqlMODIFIED WebContent/WEB-INF/view/mypru/partialSurrender/chbstaView.jspMODIFIED WebContent/WEB-INF/view/mypru/policy/detail/policy_basic.jspMODIFIED | sesv WebContent/WEB-INF/view/mypru/policy/financialSection/basic_value.jsp 根据用户以下需求 Show Basic Plan Values: Show guaranteed cash value, terminal bonus face value and terminal bonus cash value Hide reversionary bonus and special bonus 注意: 其中terminal bonus face value and terminal bonus cash value 这两个value的code要从cv_trad.jsp里面其中 copy过来,其中判断条件在aessvc的LifePolicyBusinessBean里面加了 sesv WebContent/WEB-INF/view/mypru/policy/financialSection/loanSection/loan_section_template_a.jspMODIFIED 根据用户以下需求 Show Loan Hide Reduced paid-up (RPU) amount 隐藏掉就ok了 | ready | 100% deployment progress | 2023-05-22 | 2023-05-24 | 2023-05-25 | 2023-05-29 | 2023-06-05 |  |  | 2023-07-04
20230706 | MYPRU | 1249 | https://jira.pruconnect.net/browse/PHKLMYPRUDENTIAL-1249 | [PPP220700800] PIC New Product – PVP (PWSP revamp)--JIRA1249-12 Show policy details | Heaton Liu | AES | 220700800-10 | store/220700800-10.lstADDED store/pw_gcv_basic.sqlADDED store/ste_gcv_basi.sqlADDED store/bl_cvf_boy.sqlMODIFIED store/sp_aes_fin_basic.sqlMODIFIED | 在mypru的页面保单详情,twiny说数据不对,经过调查,发现call pvp的时候报错,通知了dba同步了数据过来,所以改了以下三个sql | ready | 100% deployment progress | 2023-05-22 | 2023-05-24 | 2023-05-25 | 2023-05-29 | 2023-06-05 |  |  | 2023-07-04
20230706 | MYPRU | 1249 | https://jira.pruconnect.net/browse/PHKLMYPRUDENTIAL-1249 | [PPP220700800] PIC New Product – PVP (PWSP revamp)--JIRA1249-12 Show policy details | Heaton Liu | AESSVC | 220700800-10 | aessvc src/com/pru/hk/policy/life/spring/bean/FinancialBusinessBean.javaMODIFIED | aessvc src/com/pru/hk/policy/life/spring/bean/LifePolicyBusinessBean //这里加条件 //这里是call回来的 } else if ("TB_FV".equals(bonusType)) { if ("PMIH".equals(prodCd) ¦¦ "PVP".equals(prodCd) ¦¦ prodSeries.getIsCCLSeries()) { resultBonus.setDisplayBonusTable("Y"); resultBonus .setDisplayTerminalBonusFaceValue("Y"); resultBonus .setTerminalBonusFaceValue(totalAmount); //这里是为了给默认值 if (prodSeries.getIsCCLSeries() ¦¦ "PMIH".equals(prodCd) ¦¦ "PVP".equals(prodCd)) { LogUtil.info(logger, szLogPrefix + "Special Handling for Terminal Bonus"); if (!"Y".equals(resultBonus.getDisplayTerminalBonusFaceValue())) { LogUtil.info(logger, szLogPrefix + "DisplayTerminalBonusFaceValue = " + resultBonus.getDisplayTerminalBonusFaceValue()); resultBonus.setDisplayBonusTable("Y"); resultBonus.setDisplayTerminalBonusFaceValue("Y"); resultBonus.setTerminalBonusFaceValue(BigDecimal.ZERO); //这里需要调查,因为call回来error,会导致给默认值0 for (int i = 0; bonusList.size() > i; i++) { BONUS bonus = bonusList.get(i); LogUtil.info(logger, szLogPrefix + "Error Code: " + bonus.getErrorCode()); | ready | 100% deployment progress | 2023-05-22 | 2023-05-24 | 2023-05-25 | 2023-05-29 | 2023-06-05 |  |  | 2023-07-04
20230706 | AES | 1249 | https://jira.pruconnect.net/browse/PHKLMYPRUDENTIAL-1249 | [PPP220700800] PIC New Product – PVP (PWSP revamp)--JIRA1249-12 Show policy details | Heaton Liu | SAES | 220700800-10 | WebContent/WEB-INF/message/epa/config.propertiesMODIFIED WebContent/WEB-INF/message/epa/config.properties.original20220715MODIFIED WebContent/WEB-INF/message/epa/config.properties.original20221112MODIFIED WebContent/WEB-INF/message/epa/config.properties.original20230101MODIFIED WebContent/WEB-INF/view/epa/quotsa/preview.jspMODIFIED | 此外,提到PVP要follow PWSP,这里全局搜索找到的也加了,备注一下 | ready | 100% deployment progress | 2023-05-22 | 2023-05-24 | 2023-05-25 | 2023-05-29 | 2023-06-05 |  |  | 2023-07-04
20230706 | MYPRU | 1249 | https://jira.pruconnect.net/browse/PHKLMYPRUDENTIAL-1249 | [PPP220700800] PIC New Product – PVP (PWSP revamp)--JIRA1249-13 Disable UPOP payment | Heaton Liu | N/A |  |  |  | ready | 100% deployment progress | 2023-05-22 | 2023-05-24 | 2023-05-25 | 2023-05-29 | 2023-06-05 |  |  | 2023-07-04
20230706 | MYPRU | 1249 | https://jira.pruconnect.net/browse/PHKLMYPRUDENTIAL-1249 | [PPP220700800] PIC New Product – PVP (PWSP revamp)--JIRA1249-14 Disable MPGS payment | Heaton Liu | N/A |  |  |  | ready | 100% deployment progress | 2023-05-22 | 2023-05-24 | 2023-05-25 | 2023-05-29 | 2023-06-05 |  |  | 2023-07-04
20230706 | MYPRU | 1249 | https://jira.pruconnect.net/browse/PHKLMYPRUDENTIAL-1249 | [PPP220700800] PIC New Product – PVP (PWSP revamp)--JIRA1249-15 FVI report | Heaton Liu | N/A |  |  |  | ready | 100% deployment progress | 2023-05-22 | 2023-05-24 | 2023-05-25 | 2023-05-29 | 2023-06-05 |  |  | 2023-07-04
20230706 | AES | 849 | https://jira.pruconnect.net/browse/PHKLAES-849 | PIC-PVP - AES enquiry page | Heaton Liu | N/A |  |  | confluence AES sample | ready | 100% deployment progress | 2023-05-22 | 2023-05-23 | 2023-05-18 | 2023-05-24 | 2023-06-05 |  |  | 2023-07-04
20230706 | AES | 851 | https://jira.pruconnect.net/browse/PHKLAES-851 | PIC-PVP - AES Basic Info page | Heaton Liu | [5 empty] | 100% deployment progress | 2023-05-22 | 2023-05-23 | 2023-05-25 |  | 2023-06-05 |  |  | 2023-07-04
20230706 | AES | 852 | https://jira.pruconnect.net/browse/PHKLAES-852 | PIC-PVP- Financial Overview | Heaton Liu | AES | 220700800-10 | ARMLET-IFX/220700800-10.sh created store/220700800-10.lst created store/220700800-10.sql created | DELETE AES_TBL_CONFIG WHERE prod_cd = 'PVP'; -- basic info INSERT INTO aes_tbl_config VALUES ('policy.detail','totalPremiumPaid',0,'PVP','','220700800-10',current); INSERT INTO aes_tbl_config VALUES ('policy.detail','deathSettlementOption',20000,'PVP','','220700800-10', current); INSERT INTO aes_tbl_config VALUES ('policy.detail','nonForfeitedOption',24000,'PVP','','220700800-10', current); --financial info INSERT INTO aes_tbl_config VALUES ('policy.fininfo','ccy',0,'PVP','','220700800-10',current); INSERT INTO aes_tbl_config VALUES ('policy.fininfo','A1',10000,'PVP','','220700800-10', current); INSERT INTO aes_tbl_config VALUES ('policy.fininfo','D2x',41000,'PVP','','220700800-10',current); INSERT INTO aes_tbl_config VALUES ('policy.fininfo','D5',45000,'PVP','','220700800-10',current); INSERT INTO aes_tbl_config VALUES ('policy.fininfo','D6',46000,'PVP','','220700800-10',current); INSERT INTO aes_tbl_config VALUES ('policy.fininfo','D12',55000,'PVP','','220700800-10',current); | ready | 100% devpolyment | 2023-05-24 | 2023-05-25 | 2023-05-22 | 2023-05-22 | 2023-06-05 |  |  | 2023-07-04
20230706 | AES | 852 | https://jira.pruconnect.net/browse/PHKLAES-852 | PIC-PVP- Financial Overview | Heaton Liu | AESSVC | 220700800-10 | src/com/pru/hk/policy/life/dao/impl/LifePolicyDaoInformixImpl.java changed src/com/pru/hk/policy/life/spring/bean/LifePolicyBusinessBean.java changed src/com/pru/hk/to/policy/life/LifePolicyTO.javachanged | aessvc call進來這裏 @WebResult(name = "return", targetNamespace = "") @RequestWrapper(localName = "getPolicy", targetNamespace = "http://www.prudential.com.hk/service/soap/LifePolicyWebService", className = "com.pru.hk.stub.aes.ws.GetPolicy") @WebMethod @ResponseWrapper(localName = "getPolicyResponse", targetNamespace = "http://www.prudential.com.hk/service/soap/LifePolicyWebService", className = "com.pru.hk.stub.aes.ws.GetPolicyResponse") public com.pru.hk.stub.aes.ws.LifePolicyTO getPolicy( @WebParam(name = "arg0", targetNamespace = "") java.lang.String arg0, @WebParam(name = "arg1", targetNamespace = "") java.lang.String arg1, @WebParam(name = "arg2", targetNamespace = "") java.lang.String arg2 ) throws PUSoapServiceFault; //這裏是封裝GrossBasicCashValue關鍵 sa封裝已經做好 src/com/pru/hk/policy/life/spring/bean/LifePolicyBusinessBean.java public LifePolicyTO getPolicy(String agentCode, String policyNo, String branchCd) throws BusinessException { !!!!!//EAI過來的封裝進policy.setGuaranteedCashValue(financial.getGrossBasicCashValue()); lifePolicyTO = getFinancial(policyNo, lifePolicyTO, policy, rowlist); //EAI過來的封裝進lifePolicyTO.setGuaranteedCashValue( PUUtil.decToThousandZero( CommonUtil.convertBigDecimal(financialTag.getGrossBasicCashValue()), 2) ); updatePLSeriesFinancialInfoWithEAI(policyNo, lifePolicyTO); //sa封裝可能是這裏call sp_aes_fin_info('000020218840','O') lifePolicyTO.setGuaranteedAmount(PUUtil.decToThousandZero( financialInfo.getSumAssured().getBasic(), 2)); //sa封裝可能是這裏 來自EAI lifePolicyTO.setGuaranteedAmount( PUUtil.decToThousandZero( CommonUtil.convertBigDecimal(financialTag.getBasicSA()), 2) ); //cash value / face value 來源,這裏setup prodcode src/com/pru/hk/policy/life/dao/impl/LifePolicyDaoInformixImpl.java if ("PMIH".equals(prodCd) ¦¦ "CCL".equals(prodCd) ¦¦ "CCL2".equals(prodCd) ¦¦ "CCL2H".equals(prodCd) ¦¦ "CCL3".equals(prodCd) ¦¦ "CCL3H".equals(prodCd) ¦¦ "CIR".equals(prodCd) ¦¦ "CIRH".equals(prodCd) ¦¦ "CIR2".equals(prodCd) ¦¦ "CIR2H".equals(prodCd) ¦¦ "CIP".equals(prodCd) ¦¦ "CIPH".equals(prodCd) ¦¦ "CIP2".equals(prodCd) ¦¦ "CIP2H".equals(prodCd) ¦¦ "LFREESP".equals(prodCd) ¦¦ "LFREE".equals(prodCd) ¦¦ "P8S".equals(prodCd) ¦¦ "PVP".equals(prodCd) ) { resultBonus.setTerminalBonusFaceValue(totalAmount); } if ("PMIH".equals(prodCd) ¦¦ "CCL".equals(prodCd) ¦¦ "CCL2".equals(prodCd) ¦¦ "CCL2H".equals(prodCd) ¦¦ "CCL3".equals(prodCd) ¦¦ "CCL3H".equals(prodCd) ¦¦ "CIR".equals(prodCd) ¦¦ "CIRH".equals(prodCd) ¦¦ "CIR2".equals(prodCd) ¦¦ "CIR2H".equals(prodCd) ¦¦ "CIP".equals(prodCd) ¦¦ "CIPH".equals(prodCd) ¦¦ "CIP2".equals(prodCd) ¦¦ "CIP2H".equals(prodCd) ¦¦ "LFREESP".equals(prodCd) ¦¦ "LFREE".equals(prodCd) ¦¦ "P8S".equals(prodCd) ¦¦ "PVP".equals(prodCd) ) { resultBonus.setTerminalBonusCashValue(totalAmount); } if ("CCL".equals(prodCd) ¦¦ "CCL2".equals(prodCd) ¦¦ "CCL2H".equals(prodCd) ¦¦ "CCL3".equals(prodCd) ¦¦ "CCL3H".equals(prodCd) ¦¦ "CIR".equals(prodCd) ¦¦ "CIRH".equals(prodCd) ¦¦ "CIR2".equals(prodCd) ¦¦ "CIR2H".equals(prodCd) ¦¦ "PCC".equals(prodCd) ¦¦ "PCCH".equals(prodCd) ¦¦ "CIM2".equals(prodCd) ¦¦ "CIM2H".equals(prodCd) ¦¦ "CIM".equals(prodCd) ¦¦ "CIMH".equals(prodCd) ¦¦ "CIM3".equals(prodCd) ¦¦ "BCIM3".equals(prodCd) ¦¦ "CIM3H".equals(prodCd) ¦¦ "BCIM3H".equals(prodCd) ¦¦ "CIM3M".equals(prodCd) ¦¦ "BCIM3M".equals(prodCd) ¦¦ "CIM3HM".equals(prodCd) ¦¦ "BCIM3HM".equals(prodCd) ¦¦ "PMIH".equals(prodCd) ¦¦ "CIP".equals(prodCd) ¦¦ "CIPH".equals(prodCd) ¦¦ "CIP2".equals(prodCd) ¦¦ "CIP2H".equals(prodCd) ¦¦ "LFREESP".equals(prodCd) ¦¦ "LFREE".equals(prodCd) ¦¦ "P8S".equals(prodCd) ¦¦ "PVP".equals(prodCd) ) { if (resultBonus.getTerminalBonusFaceValue() == null) { resultBonus.setTerminalBonusFaceValue(BigDecimal.ZERO); } if (resultBonus.getTerminalBonusCashValue() == null) { resultBonus.setTerminalBonusCashValue(BigDecimal.ZERO); } } | ready | 100% devpolyment | 2023-06-19: 2023-05-24; 2023-06-19: 2023-05-25; 2023-06-21: 2023-06-05; 2023-07-01: 2023-07-04
20230706 | AES | 853 | https://jira.pruconnect.net/browse/PHKLAES-853 | PIC-PVP- AES Alteration Quotation | Heaton Liu | N/A | N/A |  |  | ready | 100% devpolyment | 2023-06-19: 2023-05-26; 2023-06-19: 2023-05-31; 2023-06-21: 2023-06-05; 2023-07-01: 2023-07-04
20230717 | AES | 945 | https://jira.pruconnect.net/browse/PHKLAES-945 | IN02397912 SWB duplicate in finance summay | Heaton Liu | SAES | IN02397912 | WebContent/WEB-INF/view/proposal_policy/policy_details.jspMODIFIED | C2 代码重复，删了即可 | ready | 100% deployment progress | 2023-06-19: 2023-07-05; 2023-06-19: 2023-07-06; 2023-07-01: 2023-08-14
20230717 | MYPRU | 1393 | https://jira.pruconnect.net/browse/PHKLMYPRUDENTIAL-1393 | VFP Revamp - Multiple Treatment sure | Heaton Liu | AES | 221201100-01 | NA | 修改條件，根據條件顯示或隱藏"安心醫服務詳情"的鏈接 | ready | 100% devpolyment | 2023-07-01: 2023-08-14
20230717 | AES | 948 | https://jira.pruconnect.net/browse/PHKLAES-948 | Treatment Sure - Multiple Medical Plans for Treatment Sure eligibility checking page | Heaton Liu | AES | 221201100-01 | ARMLET-IFX/221201100-01.shADDED store/221201100-01.lstADDED store/sp_cep_get_med_pol_dtl.sqlMODIFIED | Alvin提出改需求 if anni date < 2024.07.01 or today+1 year < anni date then error->hidden (vfp vfpp vfpq vfpr) otherwise pass 如果多个benfcode存在的情况下, 比如有vipr和vfpr,如果vfpr除了error,那么vipr也要显示. 如果只有 vfp/vfpp/vfpr/vfpq,其中一个出了error不显示 | ready | 100% devpolyment | 2023-07-01: 2023-08-14
20230717 | AES | 948 | https://jira.pruconnect.net/browse/PHKLAES-948 | Treatment Sure - Multiple Medical Plans for Treatment Sure eligibility checking page | Heaton Liu | SAES | 221201100-01 | WebContent/WEB-INF/message/cepPolicy/locale_en.properties WebContent/WEB-INF/message/cepPolicy/locale_zh.properties WebContent/WEB-INF/view/CEPPolicy/cep_enquiry.jsp | 删除E006 | ready | 100% devpolyment | 2023-07-01: 2023-08-14
20230720 | AES | 953 | https://jira.pruconnect.net/browse/PHKLAES-953 | Fix Treatment Sure sql | Heaton Liu | AES | 221201100-03 | ARMLET-IFX/221201100-03.shADDED store/221201100-03.lstADDED store/sp_cep_get_med_pol_dtl.sqlMODIFIED | production issue:存储过程修改 优化sql sp_cep_get_med_pol_dtl.sql | ready | 100% devpolyment | 2023-07-01: 2023-08-14
20230720 | AES | 942 | https://jira.pruconnect.net/browse/PHKLAES-942 | PIC-FEA-able to retrieve the FEA the 3rd customer letter - Submitted Documents and Images | Simon Liao | AES | SR02365686 | store/SR02365686.lst created ARMLET-IFX/SR02365686.sh created store/SR02365686.sql created | 此jira作为form id SQL项目模板AES | ready | user sign off done | 2023-06-30 | 2023-06-30 | 2023-06-30 | 2023-06-30 | 2023-06-30 |  |  | 2023-07-04
20230724 | MYPRU | 1361 | https://jira.pruconnect.net/browse/PHKLMYPRUDENTIAL-1361 | [myPrudential] Add new letter for FEA fund | Simon Liao | AESSVC | 221201301 | src/com/pru/hk/client/eai/dao/impl/EstatementEaiDaoImpl.java changed C:\lxw\tasks\20230619 JIRA1361 Add new letter for EGC\result\a037-aessvc\src\com\pru\hk\client\life\spring\bean\EstatementBusinessBean.java changed (add pmap000220 in type list) C:\lxw\tasks\20230619 JIRA1361 Add new letter for EGC\result\a037-aessvc\src\com\pru\hk\client\eai\dao\impl\EstatementEaiDaoImpl.java changed (add pmap000220 in isLetterType) | 此jira作为form id SQL项目模板MYPRU: （其實只要修改EstatementEaiDaoImpl.java 添加新的來源于prulife EAI log 的 rec_type 標簽裏面的英文内容到這個程序的180行下面，就可以了。其它的不用加否則mypru會看到2個重複的LETTER ）前面這句話是後面JIRA1381發現的，所以這個JIRA1361除了修改上面180行，還添加了2個地方，結果是會看到重複的LETTER，目前user沒提出來，暫時不改回去。 remember next time if add new doctype name in MYPRU, "CREATION OF NEW SHARE CLASS IN THE FUND CORRESPONDING TO EMERGING EUROPE MIDDLE EAST AND AFRICA FUND" //PHKLMYPRUDENTIAL-1361 ) defined in private static final ArrayList<String> LETTER_LIST in EstatementEaiDaoImpl.java need follow EAI respoone reportType tab : <ReportType>CREATION OF NEW SHARE CLASS IN THE FUND CORRESPONDING TO EMERGING EUROPE MIDDLE EAST AND AFRICA FUND</ReportType>, otherwise, if(LETTER_LIST.contains(rs.getString("ReportType").trim() 【here condition not fatisfy, view.jsp is not able to get field population as listed below:】) && ! policyDetail.getPolicy().getHkContractHeader().getPoliceStateCd().contains("OUTFORCE")){ ss.setTrueType(policyType); logger.info("20230717 JIRA1361 ---8"); if(PRUConstant.ESTATEMENT_POLICY_TYPE_LETTER.equals(policyType)) { ss.setStatementType(rs.getString("doc_type_code").trim()); ss.setDocID(rs.getString("docid").trim()); ss.setPolicyNo(rs.getString("pol_no").trim()); ss.setStatementName(rs.getString("ReportType").trim()); ss.setDocumentName(rs.getString("ReportType").trim()); // JIRA1361 test start | ready | user sign off done | 2023-06-12 | 2023-06-13 | 2023-06-12 | 2023-06-13 | 2023-06-13 | 2023-06-26 | 2023-06-28 | 2023-07-01
N/A | AES | 922 | https://jira.pruconnect.net/browse/PHKLAES-922 | saes polaris | Yu Sheng Chen | SAES | polaris_integrity_fix | ProposalPolicyController.java |  |  | (53/53) deployment progress | 2023-06-19: 2023-05-17; 2023-06-19: 2023-06-28; 2023-06-19: 2023-05-17; 2023-06-19: 2023-06-28
N/A | AES | 922 | https://jira.pruconnect.net/browse/PHKLAES-922 | nexus fix | Yu Sheng Chen | SAES | polaris_integrity_fix | ProposalPolicyController.java |  |  | (0/2) deployment progress | 2023-06-19: 2023-06-28; 2023-06-19: 2023-07-14; 2023-06-19: 2023-06-28
20230817 | MYPRU | 1398 | https://jira.pruconnect.net/browse/PHKLMYPRUDENTIAL-1398 | Add refresh SI letter | Simon Liao | AESSVC | 221201301-30 | a037-aessvc\src\com\pru\hk\client\life\spring\bean\EstatementBusinessBean.java changed (add SALBON in type list) a037-aessvc\src\com\pru\hk\client\eai\dao\impl\EstatementEaiDaoImpl.java changed (add SALBON in isLetterType) |  | ready | waiting uat-signed-off | 2023-07-14 | 2023-07-14 | 2023-07-17 | 2023-08-10 | 2023-08-11 |  |  | 2023-08-14
20230817 | AES | 854 | https://jira.pruconnect.net/browse/PHKLAES-854 | PIC-PVP-add form code in AES- Submitted Documents and Image | Heaton Liu | AES | 220700800-20 | ARMLET-IFX/220700800-20.sh store/220700800-20.lst store/220700800-20.sql | confluence form id 模板 Agency, Broker, SCB--for 香港, channel:ABEIJK Macau--for 澳门channel:M | ready | already signed off | 2023-06-08 | 2023-06-08 | 2023-06-08 | 2023-06-08 | 2023-08-11 |  |  | 2023-08-14
20230817 | AES | 928 | https://jira.pruconnect.net/browse/PHKLAES-928 | PPP230200200 - My Achievement Overseas Convention 2024 | Heaton Liu | SAES | 230200300 | WebContent/WEB-INF/message/aes/achievement_en.propertiesMODIFIED WebContent/WEB-INF/message/aes/achievement_zh.propertiesMODIFIED WebContent/WEB-INF/view/myachievement/travel/travel_report.jspMODIFIED WebContent/WEB-INF/view/myachievement/travel/travel_subreport.jspMODIFIED | 個人報告level 1和4不用改 2是100%改hardcode 3是隐藏 注意手机端和电脑端都要改 組員報告 level 手機端,電腦端都刪掉 | ready | waiting uat-signed-off | 2023-07-10 | 2023-07-13 | 2023-07-10 | 2023-08-07 | 2023-08-11 |  |  | 2023-08-14
20230817 | AES | 937 | https://jira.pruconnect.net/browse/PHKLAES-937 | PPP230200300 - Hide "H&P" field in 2023 Honours Club | Heaton Liu | SAES | 230200300 | WebContent/WEB-INF/view/myachievement/award/progress_report.jsp WebContent/WEB-INF/view/myachievement/award/progress_subreport.jspMODIFIED | 注意手机端和电脑端都要改 | ready | waiting uat-signed-off | 2023-07-10 | 2023-07-13 | 2023-07-10 | 2023-08-07 | 2023-08-11 |  |  | 2023-08-14
20230817 | AES | 956 | https://jira.pruconnect.net/browse/PHKLAES-956 | PA - eReply enhancement project - closing the page automatically after submission | Heaton Liu | SAES | SR02434383 | WebContent/WEB-INF/message/eupload/locale_en.propertiesMODIFIED WebContent/WEB-INF/message/eupload/locale_zh.propertiesMODIFIED WebContent/WEB-INF/view/eupload/upload.jspMODIFIED WebContent/WEB-INF/view/eupload/upload_juvenile.jspMODIFIED | 把上傳成功的窗口確定按鈕改成 '確定並關閉此分頁', 并且跳轉到指定頁面basic information 改hardcode,改跳轉的function 失敗的case改hardcode, "或" | ready | already signed off | 2023-07-10 | 2023-07-13 | 2023-07-10 | 2023-07-11 | 2023-08-11 |  |  | 2023-08-14
20230817 | AES | 926 | https://jira.pruconnect.net/browse/PHKLAES-926 | AES TT e-form Enhancement | Heaton Liu | SAES | SR02365686 | WebContent/WEB-INF/message/eCashier/locale_en.propertiesMODIFIED WebContent/WEB-INF/message/eCashier/locale_zh.propertiesMODIFIED WebContent/WEB-INF/view/eCashier/eCashier_js.jspMODIFIED src/com/pru/hk/aes/controller/agent/eCashier/ECashierController.javaMODIFIED src/com/pru/hk/aes/controller/BaseController.javaMODIFIED src/com/pru/hk/aes/to/policy/life/LifeAgentTO.javaMODIFIED | 1. 改hardcode 2. 把带条件的hardcode去掉,让channel B 进来 3. 改hardcode 4. 把带条件的channel A/M 去掉,remark去掉 5. 改hardcode 6.accessroles代表是channel,user說a能拿到proposal,B/M拿不到,我把B和M都加進去了role裏面 import org.apache.log4j.Logger; private final Logger logger = Logger.getLogger(this.getClass()); | ready | already signed off | 2023-07-10 | 2023-07-13 | 2023-07-10 | 2023-07-11 | 2023-08-11 |  |  | 2023-08-14
20230817 | AES | 935 | https://jira.pruconnect.net/browse/PHKLAES-935 | Modify AES Commission summary display for PWL item | Simon Liao | AES | 211202200 | src/com/pru/aes/agent/db/ValueObjectConvertor.java changed | 模板:這裏是第一次修改了AES庫的aes_src， 需要restart aesuat CR no.: CR00063030 | ready | already signed off | 2023-07-10 | 2023-07-13 | 2023-07-10 | 2023-07-11 | 2023-08-11 |  |  | 2023-08-14
20230817 | AES | 962 | [PHKLAES-962] Claim Information - Update text in Payee if Dealth Claim - Jira (pruconnect.net) | Claim Information - Update text in Payee if Dealth Claim | Yu Sheng Chen | SAES | IN02415015 | WebContent/WEB-INF/message/aes/locale_en.properties changed WebContent/WEB-INF/message/aes/locale_zh.properties changed WebContent/WEB-INF/view/proposal_policy/claim_history.jsp changed | 添加if语句对页面显示内容进行判断 | ready | user is testing | 2023-08-10 | 2023-08-11 | 2023-08-10 | 2023-08-10 | 2023-08-11 |  |  | 2023-08-14
20230817 | AES | 957 | https://jira.pruconnect.net/browse/PHKLAES-957 | Support under assessment / 處理中 in Claim history | Simon Liao | SAES | PPP/ITJR-Pending-Approval_JIRA957 | Epick link: 200202300 a037-saes\WebContent\WEB-INF\view\proposal_policy\claim_history.jsp | add regular expression to support "under assessment / 處理中" | ready | waiting uat-signed-off | 2023-07-24 | 2023-07-24 | 2023-07-24 | 2023-07-24 | 2023-08-11 |  |  | 2023-08-14
20230817 | MYPRU | 1406 | [PHKLMYPRUDENTIAL-1406] Support under assessment / 處理中 in Claim history - Jira (pruconnect.net) | Support under assessment / 處理中 in Claim history | Heaton Liu | SESV | PPP/ITJR-Pending-Approval_JIRA957 | WebContent/WEB-INF/view/mypru/eclaims/claimsDetails/index.jspMODIFIED | add regular expression to support "under assessment / 處理中" | ready | waiting uat-signed-off | 2023-07-31 | 2023-08-02 | 2023-08-03 | 2023-08-04 | 2023-08-11 |  |  | 2023-08-14
20230817 | MYPRU | 1366 | https://jira.pruconnect.net/browse/PHKLMYPRUDENTIAL-1366 | [IN02365437] Enrich the error message in the registration process | Simon Liao | APPSVC | IN02365437-10 | \a074-appsvc\src\com\pru\hk\admin\maintmem\spring\bean\GiRegistrationMemberBusinessBean.java changed \a074-appsvc\src\com\pru\hk\admin\maintmem\dao\db2\impl\MaintMemberDb2DaoImpl.java changed \a074-appsvc\src\com\pru\hk\admin\maintmem\dao\db2\MaintMemberDb2Dao.java changed | old IN02365437 has conflict, create a new IN02365437-10 instead |  | waiting uat-signed-off | 2023-07-10 | 2023-07-13 | 2023-07-17 | 2023-08-10 | 2023-08-11 |  |  | 2023-08-14
20230817 | MYPRU | 1366 | https://jira.pruconnect.net/browse/PHKLMYPRUDENTIAL-1366 | [IN02365437] Enrich the error message in the registration process | Simon Liao | SCWS | IN02365437 | \a074-scws\WebContent\WEB-INF\message\member\view_zh.properties changed \a074-scws\WebContent\WEB-INF\message\member\view_en.properties changed |  |  | waiting uat-signed-off | 2023-07-10 | 2023-07-13 | 2023-07-17 | 2023-08-10 | 2023-08-11 |  |  | 2023-08-14
20230817 | MYPRU | 1407 | [PHKLMYPRUDENTIAL-1407] fix wechat batch success flag - Jira (pruconnect.net) | https://jira.pruconnect.net/browse/PHKLMYPRUDENTIAL-1407 | Alex KC Kwan | CWS | PHKLMYPRUDENTIAL-1407 | cws-batch/src/com/pru/hk/cws/batch/mypru/tasklet/WechatBindingWriter.java | bug, no need sign off and confluence documents |  | 100% deployment progress | 2023-08-11 | 2023-08-11 | 2023-08-11 |  | 2023-08-11 |  |  | 2023-08-14
20230817 | MYPRU | 1360 | https://jira.pruconnect.net/browse/PHKLMYPRUDENTIAL-1360 | Fix FVI issue of triggering twice within a short period of time | Yu Sheng Chen | AESSVC SESV | IN02361657 | sesv esv_hk/store/DB2/IN02361657.sql added stub/com/pru/hk/mypru/stub/policy/life/ws/FutureValueIllustrationAccessHistoryLogTO.java added esv_hk/store/DB2/pre-production.lst changed esv_hk/store/DB2/was9_common.lst changed stub/com/pru/hk/mypru/stub/policy/life/ws/PolicyHistSoapService.java changed src/com/pru/hk/mypru/adapter/ws/soap/SoapPolicyHistAdapter.java changed src/com/pru/hk/mypru/adapter/ws/PolicyHistAdapter.java changed src/com/pru/hk/mypru/facade/PolicyHistFacade.java changed src/com/pru/hk/mypru/web/controller/LifePolicyController.java changed src/com/pru/hk/sesv/util/DateUtil.java changed WebContent/web-INF/message/fvi/locale_en.properties changed WebContent/web-INF/message/fvi/locale_zh.properties changed WebContent/web-INF/view/mypru/policy/fvi/error_page.jsp changed src/com/pru/hk/sesv/util/XMLGregorianCalendarConverter.java changed ------aessve src/com/pru/hk/policy/life/dao/impl/FviAccessHistoryLogImpl.java added src/com/pru/hk/policy/life/dao/FviAccessHistoryLogDao.java added src/com/pru/hk/policy/life/spring/bean/FviAccessHistoryLogBusinessBean.java added src/com/pru/hk/to/policy/life/FutureValueIllustrationAccessHistoryLogTO.java added src/com/pru/hk/policy/life/service/PolicyHistService.java changed src/com/pru/hk/policy/life/ws/soap/impl/PolicyHistSoapServiceImpl.java changed src/com/pru/hk/policy/life/ws/PolicyHistSoapService.java changed |  |  | 90% devpolyment (postponed to future) | 2023-07-10 | 2023-08-07 | 2023-07-10 | 2023-08-10 | 2023-08-11 |  |  | 2023-08-14
2023XXXX | AES | 923 | https://jira.pruconnect.net/browse/PHKLAES-923 | aessvc polaris and nexus fix | Yu Sheng Chen | AESSVC |  |  |  |  | (3/320) deployment progress
20230918 | AES | 925 | https://jira.pruconnect.net/browse/PHKLAES-925 | Update auto-reply email "Renewal Enrolment Confirmation" of AES | Heaton Liu | AES | SR02365684 | templates/medical_enrol_renewal.vmMODIFIED | 這裏第一次修改了AES庫的aes_batch， 記得CICD后需要stop and start sever AES UAT: cd /home/wasadmin/wasbin9 stopServer.sh aesuat startServer.sh aesuat ---if restart successfully, will see process id is 14811320 | ready | already signed off | 2023-07-01: 2023-08-14
20230918 | AES | 927 | https://jira.pruconnect.net/browse/PHKLAES-927 | PPP230200300 - My Achievement Annual Award add Group H&P Award | Heaton Liu | AES | 230200300-927 | ARMLET-IFX/230200300-927.shADDED store/230200300-927.lstADDED store/230200300-927.sqlADDED |  | ready | already signed off | 2023-07-01: 2023-08-14
20230918 | AES | 927 | https://jira.pruconnect.net/browse/PHKLAES-927 | PPP230200300 - My Achievement Annual Award add Group H&P Award | Heaton Liu | SAES | 230200300-927 | src/com/pru/hk/aes/to/agent/life/AwardRankingReportTO.javaMODIFIED src/com/pru/hk/aes/util/StubConverter.javaMODIFIED stub/com/pru/hk/stub/aes/ws/AwardRankingReport.javaMODIFIED WebContent/WEB-INF/message/aes/achievement_en.propertiesMODIFIED WebContent/WEB-INF/message/aes/achievement_zh.propertiesMODIFIED WebContent/WEB-INF/view/myachievement/award/ranking_report.jspMODIFIED |  | ready | already signed off | 2023-07-01: 2023-08-14
20230918 | AES | 927 | https://jira.pruconnect.net/browse/PHKLAES-927 | PPP230200300 - My Achievement Annual Award add Group H&P Award | Heaton Liu | AESSVC | 230200300-927 | src/com/pru/hk/agent/eai/impl/AgentEaiImpl.javaMODIFIED src/com/pru/hk/to/agent/life/AwardRankingReport.javaMODIFIED |  | ready | already signed off | 2023-07-01: 2023-08-14
20230918 | AES | 972 | https://jira.pruconnect.net/browse/PHKLAES-972 | IN02450257 - Incorrect mapping of group medical member and upload documents in AES | Heaton Liu | SAES | IN02450257 | src/com/pru/hk/aes/controller/agent/medicalenrol/MedicalEnrolPersonalInfoController.javaMODIFIED |  | ready | already signed off
20230918 | AES | 973 | https://jira.pruconnect.net/browse/PHKLAES-973 | Fix P3S cannot get cash value issue (sp_aes_fin_basic) | Heaton Liu | AES | 220201000-10 | ARMLET-IFX/220201000-10.shADDED store/220201000-10.lstADDED store/sp_aes_fin_basic.sqlMODIFIED |  | ready | already signed off
20230918 | AES | 967 | https://jira.pruconnect.net/browse/PHKLAES-967 | PMP Enhancement - AES – for Treatment Sure and Green Channel | Simon Liao | SAES | PPP/ITJR-Pending-Approval_JIRA967 | /was9/WebSphere/AppServer/profiles/AppSrv01/installedApps/was9Cell/saes.ear/saes.war/WEB-INF/view/ecareer/main.jsp changed | Replace "Company\u2019s" by "Company's" replace "website (www.prudential.com.hk)" by "website www.prude so as to aviod XSS security voilation check | ready | prd bug no need sign off | 2023-08-22 | 2023-08-23 | 2023-08-22 | 2023-08-23 | 2023-09-08 |  |  | 2023-08-14
20230918 | AES | 958 | https://jira.pruconnect.net/browse/PHKLAES-958 | Add document image - PAIAPA | Simon Liao | AES | 220401600_PM_EGI-Product-launch | store/220401600.lst updated store/220700800-40.sql created | 被合并到JIRA927 |  | waiting uat-signed-off | 2023-08-21 | 2023-08-21 | 2023-08-21 | 2023-08-21 | 2023-08-25 |  |  | 2023-09-14
20230921 | MYPRU | 992 | https://jira.pruconnect.net/browse/PHKLMYPRUDENTIAL-992 | [PPP220401600] EGI Day 2 - Guaranteed Monthly Income History | Simon Liao | SESV | PPP220401600-10 | a074-sesv\src\com\pru\hk\mypru\web\controller\LifePolicyController.java changed a074-sesv\WebContent\resources\css\global-new.css changed a074-sesv\WebContent\resources\js\aa_policy_value_section.js changed a074-sesv\WebContent\WEB-INF\view\mypru\policy\financialSection\prai.jsp changed a074-sesv\WebContent\WEB-INF\view\mypru\policy\financialSection\pmih.jsp changed a074-sesv\WebContent\WEB-INF\view\mypru\policy\financialSection\monthlyIncomeSection\rip.jsp changed a074-sesv\WebContent\WEB-INF\view\mypru\policy\financialSection\monthlyIncomeSection\monthlyIncome_section_template_c.jsp changed a074-sesv\WebContent\WEB-INF\view\mypru\policy\financialSection\monthlyIncomePaymentHistoryOverlay.jsp created a074-sesv\WebContent\WEB-INF\view\mypru\policy\detail\monthly_income_payment_history.jsp created a074-sesv\WebContent\WEB-INF\conf\nav\mypru_nav.xml changed uat\a074-sesv\WebContent\resources\js\monthly_income_payment_history.js created |  | ready | already signed off | 2023-08-22 | 2023-08-23 | 2023-08-22 | 2023-09-06 | 2023-09-08 |  |  | 2023-08-14
20230921 | MYPRU | 1408 | https://jira.pruconnect.net/browse/PHKLMYPRUDENTIAL-1408 | Enhance benefit schedule retrieving logic | Yu Sheng Chen | AESSVC SESV | SR02421679 | src/com/pru/hk/policy/life/dao/impl/PolicyDaoInformixImpl.java changed src/com/pru/hk/policy/life/spring/bean/BenefitBusinessBean.java changed esv_hk/store/informix/pre-production.lst changed esv_hk/store/informix/SP_ESERV_GET_PL_BENF_NAME.sql changed esv_hk/store/informix/SP_ESERV_GET_POLICY_BENEFIT.sql changed esv_hk/store/informix/was9_common.lst changed src/com/pru/hk/mypru/web/controller/LifePolicyController.java changed WebContent/WEB-INF/view/mypru/policy/detail/my_coverage.jsp changed |  |  | already signed off | 2023-06-19: 2023-08-18; 2023-06-19: 2023-08-22; 2023-06-19: 2023-08-21
20230930 | MYPRU | 1381 | https://jira.pruconnect.net/browse/PHKLMYPRUDENTIAL-1381 | PIC Day 2 - add new letter for letter code EGI_RMD, EGI_RMD_MI and EGI_PAYMENT_REJ | Simon Liao | AESSVC | PPP220401600-10-EGI | a037-aessvc\src\com\pru\hk\client\eai\dao\impl\EstatementEaiDaoImpl.java changed \a037-aessvc\src\com\pru\hk\client\life\spring\bean\EstatementBusinessBean.java changed | 最后删除了:EstatementEaiDaoImpl.java 的line 310 Boolean isLetterType = (PRUConstant.ESTATEMENT_POLICY_TYPE_LETTER + ";" + "CHICOL;IMNCOF;IMNOPT;IMNCFF;pmap000217;pmap000218;pmap000219 只保留这个程序的line180 就是按照EAI return的文字： "Unsuccessful Monthly Income payment by Direct Deposit (to PDA)", //PHKLMYPRUDENTIAL-1381 EstatementBusinessBean.java 的 line 1000 typeList.add("pmap000217"); //JIRA1381 typeList.add("pmap000218"); //JIRA1381 typeList.add("pmap000219"); //JIRA1381 否则会重复显示LETTER | ready | user is testing | 2023-08-18 | 2023-08-22 | 2023-08-21 | 2023-09-12 |  |  |  | 2023-08-14
20230930 | MYPRU | 1411 | https://jira.pruconnect.net/browse/PHKLMYPRUDENTIAL-1411 | Removal of GBA medical network from the top menu | Simon Liao | SESV | 230500600 | a074-sesv\WebContent\WEB-INF\conf\nav\mypru_nav.xml changed | local folder: prd issue P5SU | ready | user is testing | 2023-08-18 | 2023-08-22 | 2023-08-21 | 2023-09-12 |  |  |  | 2023-08-14
20230930 | MYPRU | 1420 | https://jira.pruconnect.net/browse/PHKLMYPRUDENTIAL-1420 | Show Sum Assured as "N/A ^" for P5SU in My Policies page | Simon Liao | SESV | 230500600 | a074-sesv\WebContent\WEB-INF\view\mypru\policy\savingsProtectionRevamp.jsp | 被合并到JIRA1411 | ready | user is testing | 2023-08-18 | 2023-08-22 | 2023-08-21 | 2023-09-12 |  |  |  | 2023-08-14
20230930 | MYPRU | 1409 | https://jira.pruconnect.net/browse/PHKLMYPRUDENTIAL-1409 | Medical repricing regression test for FVI page, PMP and MLP | Heaton Liu | N/A | N/A | regression test, deploy no needed | N/A | N/A | N/A | 2023-07-01: 2023-08-14
20230930 | AES | 941 | https://jira.pruconnect.net/browse/PHKLAES-941 | PIC-EGI-Day 1.1 - MI & new letters in AES | Simon Liao | AES | 220401600_PM_EGI-Product-launch | ARMLET-IFX/220401600.sh created store/220401600.lst created store/220401600.sql created | 被合并到JIRA940 | N/A | already signed off | 2023-07-03 | 2023-07-05 | 2023-08-18 |  | 2023-08-25 |  |  | 2023-09-14
20230930 | AES | 955 | https://jira.pruconnect.net/browse/PHKLAES-955 | PIC-PVP-add form code in AES (Oct-2023) - Submitted Documents and Images | Simon Liao | AES | 220401600_PM_EGI-Product-launch | store/220401600.lst updated store/220700800-30.sql created | 被合并到JIRA940 | N/A | already signed off | 2023-08-21 | 2023-08-21 | 2023-08-21 | 2023-08-21 | 2023-08-25 |  |  | 2023-09-14
20230930 | AES | 963 | https://jira.pruconnect.net/browse/PHKLAES-963 | Medical Repricing 2023 - Add new SIF form - Submitted Documents and Images | Heaton Liu | AES | 230500600-963 | store/230500600-963.sql | 被合并到JIRA940 | ready | already signed off | 2023-07-01: 2023-08-14
20230930 | AES | 940 | https://jira.pruconnect.net/browse/PHKLAES-940 | PMP Enhancement - AES – for Treatment Sure and Green Channel | Heaton Liu | AES | 230500600 | ARMLET-IFX/230500600.shADDED store/230500600.lstADDED store/sp_cep_get_med_pol.sqlMODIFIED store/sp_cep_get_med_pol_dtl.sqlMODIFIE |  |  | already signed off | 2023-07-01: 2023-08-14
20230930 | AES | 940 | https://jira.pruconnect.net/browse/PHKLAES-940 | PMP Enhancement - AES – for Treatment Sure and Green Channel | Heaton Liu | SAES | 230500600 | stub/com/pru/hk/stub/aes/ws/ceppolicy/CEPPolicy.javaMODIFIED WebContent/WEB-INF/message/cepPolicy/locale_en.propertiesMODIFIED WebContent/WEB-INF/message/cepPolicy/locale_zh.propertiesMODIFIED WebContent/WEB-INF/view/CEPPolicy/cep_enquiry.jspMODIFIED |  |  | already signed off | 2023-07-01: 2023-08-14
20230930 | AES | 940 | https://jira.pruconnect.net/browse/PHKLAES-940 | PMP Enhancement - AES – for Treatment Sure and Green Channel | Heaton Liu | AESSVC | 230500600 | src/com/pru/hk/policy/life/dao/impl/CEPPolicyDaoImpl.javaMODIFIED src/com/pru/hk/to/policy/ceppolicy/CEPPolicy.javaMODIFIED |  |  | already signed off | 2023-07-01: 2023-08-14
20230930 | AES | 976 | https://jira.pruconnect.net/browse/PHKLAES-976 | pentest RITSEPT-8414 | Yu Sheng Chen | AES | pentest-2023 | jsp/index.jsp changed |  |  | NA | 2023-07-01: 2023-08-14
20231106 | MYPRU | 1426 | https://jira.pruconnect.net/browse/PHKLMYPRUDENTIAL-1426 | EGI FVI page | Simon Liao | SESV | PPP220401600-EGI-10 | esv_hk/store/informix/220401600.sql created WebContent/WEB-INF/message/fvi/locale_en.properties changed WebContent/WEB-INF/message/fvi/locale_zh.properties changed WebContent/WEB-INF/view/mypru/policy/fvi/template/shp_11.jsp created esv_hk/store/informix/pre-production.lst changed esv_hk/store/informix/was9_common.lst changed | refer to shp_09.jsp | ready | already signed off | 2023-10-07 | 07/13/2023 | 2023-10-07 | 2023-10-11 | 2023-11-01 | 2023-11-01 |  | 2023-11-03
20231106 | MYPRU | 1425 | https://jira.pruconnect.net/browse/PHKLMYPRUDENTIAL-1425 | P8S FVI page | Yu Sheng Chen | SESV | PPP220401600-P8S-10 | WebContent/WEB-INF/message/fvi/locale_en.properties changed WebContent/WEB-INF/message/fvi/locale_zh.properties changed WebContent/WEB-INF/view/mypru/policy/fvi/template/wpp_23.jsp created | refer to wpp_17.jsp | ready | already signed off | 2023-10-07 | 07/13/2023 | 2023-10-08 | 2023-10-11 | 2023-11-01 | 2023-11-01 |  | 2023-11-03
20231106 | AES | 989 | https://jira.pruconnect.net/browse/PHKLAES-989 | [PIC Day 1.1] P8S - AES Future Value Illustration (FVI) | Yu Sheng Chen | SAES | PPP220401600-P8S-10 |  |  | ready | already signed off
20231106 | AES | 988 | https://jira.pruconnect.net/browse/PHKLAES-988 | [AES day1.1] EGI Future Value Illustration | Yu Sheng Chen | SAES | PPP220401600-EGI-10 |  |  | ready | already signed off
20231123 | AES | 978 | https://jira.pruconnect.net/browse/PHKLAES-978 | 2023 AT&C part2 | Heaton Liu | SAES | 230179500 | src/com/pru/hk/aes/adapter/impl/soap/MedicalEnrolAdapterSoapImpl.javaMODIFIED src/com/pru/hk/aes/adapter/MedicalEnrolAdapter.javaMODIFIED src/com/pru/hk/aes/controller/agent/medicalenrol/MedicalEnrolBaseController.javaMODIFIED src/com/pru/hk/aes/controller/agent/medicalenrol/MedicalEnrolConstants.javaMODIFIED src/com/pru/hk/aes/controller/agent/medicalenrol/MedicalEnrolStaffRecordController.javaMODIFIED src/com/pru/hk/aes/controller/model/agent/medicalenrol/MedicalEnrolStaffRecordForm.javaMODIFIED src/com/pru/hk/aes/facade/MedicalEnrolFacade.javaMODIFIED src/com/pru/hk/aes/validator/agent/medicalenrol/MedicalEnrolBaseValidator.javaMODIFIED src/com/pru/hk/aes/validator/agent/medicalenrol/MedicalEnrolPersonalInfoValidator.javaMODIFIED stub/com/pru/hk/stub/agent/ws/medicalenrol/MedicalEnrolAppl.javaMODIFIED stub/com/pru/hk/stub/agent/ws/medicalenrol/MedicalEnrolSoapService.javaMODIFIED WebContent/WEB-INF/message/medicalenrol/error_en.propertiesMODIFIED WebContent/WEB-INF/message/medicalenrol/error_zh.propertiesMODIFIED WebContent/WEB-INF/message/medicalenrol/locale_en.propertiesMODIFIED WebContent/WEB-INF/message/medicalenrol/locale_zh.propertiesMODIFIED WebContent/WEB-INF/view/medicalenrol/agent/personal_info.jspMODIFIED WebContent/WEB-INF/view/medicalenrol/agent/submit.jspMODIFIED WebContent/WEB-INF/view/medicalenrol/agent/summary.jspMODIFIED WebContent/WEB-INF/view/medicalenrol/agent/upload.jspMODIFIED WebContent/WEB-INF/view/medicalenrol/staff/record.jspMODIFIED WebContent/WEB-INF/view/medicalenrol/staff/summary.jspMODIFIED |  |  | user is testing | 2023-10-09 | 2023-11-10 | 2023-10-09 | 2023-11-03 | 2023-11-10 | 2023-11-10 |  | 2023-11-21
20231123 | AES | 978 | https://jira.pruconnect.net/browse/PHKLAES-978 | 2023 AT&C part2 | Heaton Liu | AESSVC | 230179500 | src/com/pru/hk/agent/dao/impl/MedicalEnrolDaoImpl.javaMODIFIED src/com/pru/hk/agent/dao/MedicalEnrolDao.javaMODIFIED src/com/pru/hk/agent/service/MedicalEnrolService.javaMODIFIED src/com/pru/hk/agent/spring/bean/MedicalEnrolBusinessBean.javaMODIFIED src/com/pru/hk/agent/ws/soap/impl/MedicalEnrolSoapServiceImpl.javaMODIFIED src/com/pru/hk/agent/ws/MedicalEnrolSoapService.javaMODIFIED src/com/pru/hk/to/agent/medicalenrol/MedicalEnrolAppl.javaMODIFIED src/com/pru/hk/util/email/EmailHelper.javaMODIFIED WebContent/WEB-INF/velocity_template/medical_enrolment_record_return_as_draft.vmADDED |  |  | user is testing | 2023-10-09 | 2023-11-10 | 2023-10-09 | 2023-11-03 | 2023-11-10 | 2023-11-10 |  | 2023-11-21
20231123 | AES | 978 | https://jira.pruconnect.net/browse/PHKLAES-978 | 2023 AT&C part2 | Heaton Liu | AES | 230179500 | script/230179500.shADDED store/230179500.lstADDED store/230179500.sqlADDED | 由於Db問題，Alex手動在prod更新sql |  | user is testing | 2023-10-09 | 2023-11-10 | 2023-10-09 | 2023-11-03 | 2023-11-10 | 2023-11-10 |  | 2023-11-21
20231123 | MYPRU | 1434 | https://jira.pruconnect.net/browse/PHKLMYPRUDENTIAL-1434 | HKLPICD20273-13 HKLPICD20273-18 (移到JIRA1438) PIC Day 2 - PLIP Investment and Loyalty Bonus Declaration (Investment Choice Trading Transactions) | Simon Liao |  |  |  | HKLPICD20273-13 是regression test, 不需要delopy |  |  | 2023-11-06 | 2023-11-10 | 2023-11-06 | 2023-11-06 | 2023-11-16 | 2023-11-17 |  | 2023-11-21
20231123 | MYPRU | 1437 | https://jira.pruconnect.net/browse/PHKLMYPRUDENTIAL-1437 | Incorrect "Trading type" of Investment Bonus for PLIP | Simon Liao | SESV | .sh | C:\lxw\tasks\20231123 JIRA1437\result\a074-sesv\WebContent\WEB-INF\message\policydetail\view_en.properties changed C:\lxw\tasks\20231123 JIRA1437\result\a074-sesv\WebContent\WEB-INF\message\policydetail\view_zh.properties changed C:\lxw\tasks\20231123 JIRA1437\result\a074-sesv\esv_hk\store\informix\SP_ESERV_ENQUIRY_INVEST_TRADE.sql changed C:\lxw\tasks\20231123 JIRA1437\result\a074-sesv\esv_hk\store\informix\was9_common.lst changed C:\lxw\tasks\20231123 JIRA1437\result\a074-sesv\esv_hk\store\informix\pre-production.lst changed | This is a bug JIRA. 這裏只會滿足下面條件才會顯示： <c:when test="${productType.prodGroupCd == 'UNITLINK'}"> <jsp:include page="/WEB-INF/view/mypru/policy/financialSection/link_policy.jsp"/> </c:when> 需要Mavis找下是否有這個界面--Twiny said： 下次的JIRA有，沒確定JIRA num 20231117 delete previous changes, add change SP prulife:informix.sp_eserv_enquiry_invest_trade | ready | assigned back to user | 2023-11-06 | 2023-11-10 | 2023-11-06 | 2023-11-06 | 2023-11-16 | 2023-11-17 |  | 2023-11-21 | 復習記錄: 20231127 simon 1 time
20231123 | MYPRU | 1437 | https://jira.pruconnect.net/browse/PHKLMYPRUDENTIAL-1437 | Incorrect "Trading type" of Investment Bonus for PLIP | Simon Liao | AES | 230701900-10 目前只是保留在bitbucket，没作任何merge 到was9操作 | ARMLET-IFX/230701900-10.sh created store/230701900-10.lst created store/230701900-10.sql created | 告訴prulife去修改找 tiger WX wu，我們不需要做這個branch，只是自己測試看 | ready | assigned back to user | 2023-11-06 | 2023-11-10 | 2023-11-06 | 2023-11-06 | 2023-11-16 | 2023-11-17 |  | 2023-11-21
20231123 | MYPRU | 1430 | https://jira.pruconnect.net/browse/PHKLMYPRUDENTIAL-1430 | Customer Letter for EGSP2 Prepayment Promotion | Simon Liao | AESSVC | PPP220401600-20-EGI | C:\lxw\tasks\20231123 JRA1430 Letter for EGSP2\result\a037-aessvc\src\com\pru\hk\client\eai\dao\impl\EstatementEaiDaoImpl.java changed | 参考JIRA1381模板(程序邏輯參考JIRA1361 or JIRA1430 info， IEDA打開JIRA1398)，只要修改EstatementEaiDaoImpl.java 添加新的來源于prulife EAI log 的 rec_type 標簽裏面的英文内容到這個程序的180行下面，就可以了。其它的不用加否則mypru會看到2個重複的LETTER document name 是從EAI excel的prumap TEAM來的，讓Mavis告訴他們去添加中英文描述， 左邊的basic plan名稱，不需要sql去修改，目前修改回來了。因爲是prulife也有pol_chi_desc 和 prod_mast，而且這個basic plan是不需要修改，可以和document name不一樣。 | ready | assigned back to user | 2023-11-06 | 2023-11-10 | 2023-11-06 | 2023-11-06 | 2023-11-16 | 2023-11-17 |  | 2023-11-21 | 復習記錄: 20231127 simon 1 time
20231207 | MYPRU | 1438 | https://jira.pruconnect.net/browse/PHKLMYPRUDENTIAL-1438 | HKLPICD20273-18 PIC Day 2 - PLIP Investment and Loyalty Bonus Declaration (Policy Details) | Simon Liao | AESSVC | 230701900 | C:\lxw\tasks\20231123 JIRA1434 add PLIP config\result\a037-aessvc\src\com\pru\hk\policy\life\dao\impl\LifePolicyDaoInformixImpl.java changed 下面也要加PLIP否則拿回來的數據又沒被篩選: C:\lxw\tasks\20231123 JIRA1434 add PLIP config\result\a037-aessvc\src\com\pru\hk\policy\life\spring\bean\LifePolicyBusinessBean.java changed 下面也要修改，因爲SAES 調用AESSVC 處理 LB IB和SESV調用不是同一段 src/com/pru/hk/policy/life/spring/bean/FinancialBusinessBean.java changed | IDEA打開JIRA1434 | ready | assigned back to user | 2023-11-06 | 2023-11-10 | 2023-11-06 | 2023-11-06 | 2023-11-16 | 2023-11-17 |  | 2023-11-21 | 復習記錄: 20231127 simon 1 time
20231207 | MYPRU | 1438 | https://jira.pruconnect.net/browse/PHKLMYPRUDENTIAL-1438 | HKLPICD20273-18 PIC Day 2 - PLIP Investment and Loyalty Bonus Declaration (Policy Details) | Simon Liao | SESV | 230701900 | WebContent/WEB-INF/view/mypru/policy/financialSection/aa_policy_bonus_section.jsp changed 下面其實不需要，刪除，因爲不是這裏調用的: esv_hk/src/eservicing-hk/com/pru/eservicing/hk/modules/policy/service/util/PolicyServiceUtil.java changed | IDEA打開JIRA1434 | ready | assigned back to user | 2023-11-06 | 2023-11-10 | 2023-11-06 | 2023-11-06 | 2023-11-16 | 2023-11-17 |  | 2023-11-21 | 復習記錄: 20231127 simon 1 time
20231207 | AES | 994 | https://jira.pruconnect.net/browse/PHKLAES-994 | [PLIP][PIC Day 2] Add investment bonus and loyalty bonus under Financial Overview > Bonus(es) | Simon Liao | SAES | 230701900 | C:\lxw\tasks\20231123 JIRA1434 add PLIP config\result\a037-saes\WebContent\WEB-INF\view\proposal_policy\policy_details.jsp changed | IDEA打開JIRA994 同JIRA1438 AESSVC是同一个地方， 但SAES需要在有SWB的地方添加PLIP | ready | assigned back to user | 2023-11-06 | 2023-11-10 | 2023-11-06 | 2023-11-06 | 2023-11-16 | 2023-11-17 |  | 2023-11-21 | 復習記錄: 20231127 simon 1 time
2023XXXX | AES | 977 | https://jira.pruconnect.net/projects/PHKLAES-977 | 2023 AT&C part1 | Yu Sheng Chen |  |  |  | Duncan already finished |  |  | 2023-10-09 | 2023-11-10 | 2023-10-08 |  | 2023-11-10 | 2023-11-10 |  | 2023-11-21
20231213 | MYPRU | 1448 | https://jira.pruconnect.net/browse/PHKLMYPRUDENTIAL-1448 | EAR Fund Termination | Yu Sheng Chen | SESV | EAR_fund_blocking_202312 | WebContent/WEB-INF/message/mypru/view_en.properties updated WebContent/WEB-INF/message/mypru/view_zh.properties updated WebContent/WEB-INF/view/main/fund_select_overlay.jsp updated WebContent/WEB-INF/view/main/fund_select_overlay_remark.jsp updated WebContent/WEB-INF/view/mypru/changeDividendAllocation/view.jsp updated WebContent/WEB-INF/view/mypru/changePremiumAllocation/view.jsp updated
20240104 | MYPRU | 1427 | https://jira.pruconnect.net/browse/PHKLMYPRUDENTIAL-1427 | https://jira.pruconnect.net/browse/PHKLPRDAREV23-53 [myPrudential] Display Policy Details | Simon Liao | SESV | 231000200 | C:\lxw\tasks\20240105 JIRA1427 PIC New Product – PRDA210 PRDA220\result\new1\a074-sesv\WebContent\WEB-INF\view\mypru\policy\financialSection\basic_value.jsp changed C:\lxw\tasks\20240105 JIRA1427 PIC New Product – PRDA210 PRDA220\result\new1\a074-sesv\WebContent\WEB-INF\message\policydetail\view_en.properties changed | 邏輯參考JIRA1072 info.txt 搜索basic plan所有txt就可以找到 On Policy Details > Financial Summary: Show Basic Plan Values { Show guaranteed cash value Rename "Terminal bonus face value" to "Terminal bonus" Remove terminal bonus cash value Hide reversionary bonus and special bonus} | ready | assigned back to user | 2023-11-20 | 2023-11-28 | 2023-11-23 |  | 2023-12-04 | 2023-12-04 |  | 2024-01-01
20240104 | MYPRU | 1427 | https://jira.pruconnect.net/browse/PHKLMYPRUDENTIAL-1427 | https://jira.pruconnect.net/browse/PHKLPRDAREV23-54 [myPrudential] Enable FPS payment | Simon Liao | NA | NA |  |  | ready | assigned back to user | 2023-11-20 | 2023-11-28 | 2023-11-23 |  | 2023-12-04 | 2023-12-04 |  | 2024-01-01
20240104 | MYPRU | 1427 | https://jira.pruconnect.net/browse/PHKLMYPRUDENTIAL-1427 | https://jira.pruconnect.net/browse/PHKLPRDAREV23-55 [myPrudential] Enable MPGS payment | Simon Liao | NA | NA |  |  | ready | assigned back to user | 2023-11-20 | 2023-11-28 | 2023-11-23 |  | 2023-12-04 | 2023-12-04 |  | 2024-01-01
20240104 | MYPRU | 1427 | https://jira.pruconnect.net/browse/PHKLMYPRUDENTIAL-1427 | https://jira.pruconnect.net/browse/PHKLPRDAREV23-56 [myPrudential] Disable UPOP payment | Simon Liao | NA | NA |  |  | ready | assigned back to user | 2023-11-20 | 2023-11-28 | 2023-11-23 |  | 2023-12-04 | 2023-12-04 |  | 2024-01-01
20240104 | MYPRU | 1427 | https://jira.pruconnect.net/browse/PHKLMYPRUDENTIAL-1427 | https://jira.pruconnect.net/browse/PHKLPRDAREV23-57 [myPrudential] Disable Policy Future Value Illustration Report in 1st policy year | Simon Liao | AES | 231000200 | store/231000200.sql changed ---already deleted | 記得把修改刪除，是不需要。第一年不需要 | N/A | assigned back to user | 2023-11-20 | 2023-11-28 | 2023-11-23 |  | 2023-12-04 | 2023-12-04 |  | 2024-01-01
20240104 | MYPRU | 1427 | https://jira.pruconnect.net/browse/PHKLMYPRUDENTIAL-1427 | [PPP230702300] PIC New Product – PRDA210 / PRDA220 (PRDA revamp) PHKLPRDAREV23-118 | Simon Liao | AESSVC | 231000200 | C:\lxw\tasks\20240104 JIRA982 PIC PRDA210-220\result\a037-aessvc\src\com\pru\hk\client\eai\dao\impl\EstatementEaiDaoImpl.java changed |  | ready | assigned back to user | 2023-11-20 | 2023-11-28 | 2023-11-23 |  | 2023-12-04 | 2023-12-04 |  | 2024-01-01
20240104 | MYPRU | 1427 | https://jira.pruconnect.net/browse/PHKLMYPRUDENTIAL-1427 | [PPP230702300] PIC New Product – PRDA210 / PRDA220 (PRDA revamp) PHKLPRDAREV23-133 | Simon Liao | AESSVC | 231000200 | C:\lxw\tasks\20240104 JIRA982 PIC PRDA210-220\result\a037-aessvc\src\com\pru\hk\client\eai\dao\impl\EstatementEaiDaoImpl.java changed Later Ivan need this again | user said no need add this in LETTER. Note that SmartCare Cover need to be handled as endorsement showing under eContract instead of letter. | ready | assigned back to user | 2023-11-20 | 2023-11-28 | 2023-11-23 |  | 2023-12-04 | 2023-12-04 |  | 2024-01-01
20240104 | MYPRU | 1428 | https://jira.pruconnect.net/browse/PHKLMYPRUDENTIAL-1428 | [myPrudential] Add New Refund Letter for PRDA_TAX_REFUND | Simon Liao | N/A |  |  | duplicated task with JIRA1427---23-118 Letter | N/A | assigned back to user | 2023-11-20 | 2023-11-28 | 2023-11-23 |  | 2023-12-04 | 2023-12-04 |  | 2024-01-01
20240104 | AES | 980 | https://jira.pruconnect.net/browse/PHKLAES-980 | [PIC] PRDA210/PRDA220 - AES enquiry page | Simon Liao | N/A | NA | data is from pru-life | tell user remember test: Policy Personnel | ready | assigned back to user | 2023-11-20 | 2023-11-28 | 2023-11-23 |  | 2023-12-04 | 2023-12-04 |  | 2024-01-01
20240104 | AES | 981 | https://jira.pruconnect.net/browse/PHKLAES-981 | [PIC] PRDA210/PRDA220 - AES Basic Info page | Simon Liao | SAES | 231000200 | C:\lxw\tasks\20240104 JIRA982 PIC PRDA210-220\result\a037-saes\WebContent\WEB-INF\view\proposal_policy\policy_details.jsp changed | data is from pru-life, but need update JSP to display, because 'N' role need read table: select * from misc_code_tbl where misc_type = 'ROLE' and code = 'N' ， desc 為 DESIGNATED PERSON (SMART CARE COVER) | ready | assigned back to user | 2023-11-20 | 2023-11-28 | 2023-11-23 |  | 2023-12-04 | 2023-12-04 |  | 2024-01-01
20240104 | AES | 982 | https://jira.pruconnect.net/browse/PHKLAES-982 | [PIC] PRDA210/PRDA220 - AES Financial Overview | Simon Liao | SAES | 231000200 | C:\lxw\tasks\20240104 JIRA982 PIC PRDA210-220\result\a037-saes\WebContent\WEB-INF\view\proposal_policy\policy_details.jsp changed |  | ready | assigned back to user | 2023-11-20 | 2023-11-28 | 2023-11-23 |  | 2023-12-04 | 2023-12-04 |  | 2024-01-01
20240104 | AES | 982 | https://jira.pruconnect.net/browse/PHKLAES-982 | [PIC] PRDA210/PRDA220 - AES Financial Overview | Simon Liao | AES | 231000200 | ARMLET-IFX/231000200.sh created store/231000200.lst created store/231000200.sql created |  | ready | assigned back to user | 2023-11-20 | 2023-11-28 | 2023-11-23 |  | 2023-12-04 | 2023-12-04 |  | 2024-01-01
20240104 | AES | 982 | https://jira.pruconnect.net/browse/PHKLAES-982 | [PIC] PRDA210/PRDA220 - AES Financial Overview | Simon Liao | AESSVC | 231000200 | src/com/pru/hk/client/eai/dao/impl/EstatementEaiDaoImpl.java changed src/com/pru/hk/client/spring/bean/SesvSessionBusinessBean.javaMODIFIED changed src/com/pru/hk/policy/life/dao/impl/LifePolicyDaoInformixImpl.javaM changed src/com/pru/hk/policy/life/eai/dao/impl/PraiEaiDaoImpl.java changed src/com/pru/hk/policy/life/spring/bean/BenefitBusinessBean.java changed src/com/pru/hk/policy/life/spring/bean/FinancialBusinessBean.java changed src/com/pru/hk/policy/life/spring/bean/LifePolicyBusinessBean.javaM changed |  | ready | assigned back to user | 2023-11-20 | 2023-11-28 | 2023-11-23 |  | 2023-12-04 | 2023-12-04 |  | 2024-01-01
20240104 | AES | 983 | https://jira.pruconnect.net/browse/PHKLAES-983 | [PIC] PRDA210/PRDA220 - Alteration Quotation | Simon Liao | NA | NA |  |  | ready | assigned back to user | 2023-11-20 | 2023-11-28 | 2023-11-23 |  | 2023-12-04 | 2023-12-04 |  | 2024-01-01
20240104 | AES | 984 | https://jira.pruconnect.net/browse/PHKLAES-984 | [PIC] PRDA210/PRDA220 - Generate Proposal No. | Simon Liao | NA | NA | 記得check check 數據來源是否正確 |  | ready | assigned back to user | 2023-11-20 | 2023-11-28 | 2023-11-23 |  | 2023-12-04 | 2023-12-04 |  | 2024-01-01
20240104 | AES | 985 | https://jira.pruconnect.net/browse/PHKLAES-985 | [PIC] PRDA210/PRDA220 - Submitted Documents and Images | Simon Liao | AES | 231000200 | store/231000200.sql updated | DSMARTCARE_END_C and _E merge |  | assigned back to user | 2023-11-20 | 2023-11-28 | 2023-11-23 |  | 2023-12-04 | 2023-12-04 |  | 2024-01-01
20240104 | MYPRU | 1456 | https://jira.pruconnect.net/browse/PHKLMYPRUDENTIAL-1456 | PHKLSTODNEW-36 add PMAP000224 | Yu Sheng Chen | AESSVC | 231000200-10 | src/com/pru/hk/client/eai/dao/impl/EstatementEaiDaoImpl.java changed |  |  | already signed off
20240122 | AES | 1012 | https://jira.pruconnect.net/browse/PHKLAES-1012 | [PIC] PRDA - Add new letter for PRDA Customer Notice (Output) | Simon Liao | AES | 200202300 updated to 230702300 | ARMLET-IFX/230702300.sh created store/230702300.lst created store/230702300.sql created |  | ready | already signed off | 2024-01-03 | 2024-01-04 | 2024-01-04 | 2024-01-04 | 2024-01-15 | 2024-01-15 |  | 2024-01-18
20240205 | AES | 1015 | https://jira.pruconnect.net/browse/PHKLAES-1015 | [PIC] MIP - Loan Repayment Letters setup - Submitted Documents and Images | Simon Liao | AES | 231000200-10 | ARMLET-IFX/231000200-10.sh created store/231000200-10.lst created store/231000200-10.sql created | 加doc type 是爲了drop list能看見，參考JIRA913 test case 加wf_misc_code_tbl是爲了drop_list下面的文檔能看見,參考JIRA919 testcase | ready 注意wf_misc_code_tbl 的pmap216已經有記錄，需要咨詢一下--20240125 checked, no need add this, 20230512 added as a bug JIRA919 | already signed off | 2024-01-03 | 2024-01-04 | 2024-01-04 | 2024-01-04 | 2024-01-15 | 2024-01-15 |  | 2024-01-02
20240222 | AES | 1011 | https://jira.pruconnect.net/browse/PHKLAES-1011 | [PIC] EGP - Show Terminal Dividend under Financial Overview at 3rd Policy Year | Simon Liao | SAES | 200202300 | C:\lxw\tasks\20240219 JIRA1011\result\a037-saes\WebContent\WEB-INF\view\proposal_policy\policy_details.jsp | change this so as to display JIRA 描述的標題 | ready |  | 2024-01-03 | 2024-01-04 | 2024-01-04 | 2024-01-05 | 2024-02-05 | 2024-01-29 |  | 2024-02-15
20240222 | AES | 1011 | https://jira.pruconnect.net/browse/PHKLAES-1011 | [PIC] EGP - Show Terminal Dividend under Financial Overview at 3rd Policy Year | Simon Liao | AES | 200202300 | ARMLET-IFX/200202300.sh created store/200202300.lst created store/200202300.sql created | 目的是添加D16 sql語句標簽 | ready |  | 2024-01-03 | 2024-01-04 | 2024-01-04 | 2024-01-05 | 2024-02-05 | 2024-01-29 |  | 2024-02-15
20240222 | AES | 1011 | https://jira.pruconnect.net/browse/PHKLAES-1011 | [PIC] EGP - Show Terminal Dividend under Financial Overview at 3rd Policy Year | Simon Liao | AESSVC | 200202300 | src/com/pru/hk/policy/life/dao/impl/LifePolicyDaoInformixImpl.java changed | add EGP to get value from EAI 'TD' bonus type for terminalBonusFaceValue, 是AESSVC 第一次加入 'TD' 的配置 configuration | ready |  | 2024-01-03 | 2024-01-04 | 2024-01-04 | 2024-01-05 | 2024-02-05 | 2024-01-29 |  | 2024-02-15
20240222 | AES | 1033 | https://jira.pruconnect.net/browse/PHKLAES-1033 | IN02623041 - Missing ranking 8th in monthly agency contest | Simon Liao | AESSVC | IN02623041 | a037-aessvc\src\com\pru\hk\agent\eai\impl\AgentEaiImpl.java | comment out 3 lines |  |  | 2024-01-03 | 2024-01-04 | 2024-01-04 | 2024-01-05 | 2024-02-05 | 2024-01-29 |  | 2024-02-15
20240222 | AES | 993 | https://jira.pruconnect.net/browse/PHKLAES-993 | PHKL - PPP230600100 Enhance AES for Upload of Non-pending Document | Yu Sheng Chen Heaton Liu | AES | 230600100-Ereply |  |  | ready | already signed off
20240222 | AES | 1479 | https://jira.pruconnect.net/browse/PHKLMYPRUDENTIAL-1479 | [myPru] Add triggering points to mini survey | Heaton Liu | SESV | 220901000-miniSurvey-20240222 | ARMLET-WAS/login/surveyConfig.jsonADDED ARMLET-WAS/220901000-miniSurvey.shADDED ARMLET-WAS/pre-production.shMODIFIED ARMLET-WAS/was9_common.shMODIFIED WebContent/WEB-INF/view/mypru/changeEmailAddress/complete.jspMODIFIED WebContent/WEB-INF/view/mypru/changeMobileNumber/complete.jspMODIFIED | 在CHANGE_PHONE_NUMBER, CHANGE_EMAIL_ADDRESS 上添加mini survey 功能 關閉FUND_SWITCH,UPDATE_CONTACT 的mini survey 功能 記得修改surveyConfig.json, 這個json是配置 通過220901000-miniSurvey.sh, cd 的時候在config=Y, 會把配置覆蓋進server was9_common.sh 和 pre-production.sh 也要配, cd的時候會運行這兩個sh | ready | already signed off
20240321 | AES | 1478 | https://jira.pruconnect.net/browse/PHKLMYPRUDENTIAL-1478 | [myPru] Add back comment box to Mini Survey | Heaton Liu | SESV | 220901000-miniSurvey | src/com/pru/hk/mypru/web/controller/TransitionalSurveyController.javaMODIFIED WebContent/resources/js/revampMenu.jsMODIFIED WebContent/WEB-INF/view/mypru/changeEmailAddress/complete.jspMODIFIED WebContent/WEB-INF/view/mypru/changeMobileNumber/complete.jspMODIFIED | 點擊表情的時候,把comment的輸入框彈出來, 輸入的comment 會保存進去db裏面 通過job可以把db的東西變成最近一星期的csv(不包含今天), 通過以下命令查看csv内容 | ready | already signed off
20240314 | AES | 1505 | https://jira.pruconnect.net/browse/PHKLMYPRUDENTIAL-1505 | Show hyperlinks to view related fund pages under Financial Summary page | Heaton Liu | SESV | 220901000-20240321-01 | stub/com/pru/hk/mypru/stub/policy/life/ws/HkFinanceFundInfo.javaMODIFIED WebContent/WEB-INF/view/mypru/policy/financialSection/fund_balance.jspMODIFIED | 這個需求是要在 old investment choice balance template 下的基金名字下加兩個icons 參考New investment choice balance template 下的兩個icons 這兩個icons是兩個鏈接圖標, 第一個需要一個基金名字對應的fundCode,第二個需要基金名字對應的isinCode 後端加了邏輯通過fundname匹配fundcode, 傳到那兩個link裏面 此外, 前端的logo開始不生效, 查看investment-choices-table.css,把對應的不生效的class加在fund_balance.jsp | ready | already signed off
20240314 | AES | 1505 | https://jira.pruconnect.net/browse/PHKLMYPRUDENTIAL-1505 | Show hyperlinks to view related fund pages under Financial Summary page | Heaton Liu | AESSVC | 220901000-20240321-01 | src/com/pru/hk/policy/life/dao/impl/PolicyDaoInformixImpl.javaMODIFIED src/com/pru/hk/policy/life/spring/bean/FinancialBusinessBean.javaMODIFIED src/com/pru/hk/policy/life/to/HKFinanceFundInfo.javaMODIFIED | 這個需求是要在 old investment choice balance template 下的基金名字下加兩個icons 參考New investment choice balance template 下的兩個icons 這兩個icons是兩個鏈接圖標, 第一個需要一個基金名字對應的fundCode,第二個需要基金名字對應的isinCode 後端加了邏輯通過fundname匹配fundcode, 傳到那兩個link裏面 此外, 前端的logo開始不生效, 查看investment-choices-table.css,把對應的不生效的class加在fund_balance.jsp | ready | already signed off
20240321 | AES | 1034 | https://jira.pruconnect.net/browse/PHKLAES-1034 | Bonus Letter - New doc type to be added in Submitted Documents and Images | Simon Liao | AES | 231000200-50 | ARMLET-IFX/231000200-50.sh created store/231000200-50.lst created store/231000200-50.sql created | already CICD 參考最新模板 JIRA1015 231000200-10.sql |  | Winnie uat test done 20240209 Winnie WT Leung Hi Simon XW Liao, please help to amend the name of doc: https://jira.pruconnect.net/browse/PHKLAES-1034 EN name change to Bonus Declaration Letter 20240315 Winnie Can sign off | 2024-02-21 | 2024-02-22 | 2024-02-21 | 2024-02-21 | 2024-02-23 | 2024-02-28 | 2024-02-28
20240321 | AES | 1039 | https://jira.pruconnect.net/browse/PHKLAES-1039 | [PIC] BCIM3, BCIM3H - Add form code/letter in AES- Submitted Documents and Images | Simon Liao | AES | 231000200-60 | ARMLET-IFX/231000200-60.sh created store/231000200-60.lst created store/231000200-60.sql created |  |  | assign back to Winnie test uat not merge to uat only push and run sql 20240315 Winnie Can sign off | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 |  | 2024-03-14
20240330 | AES | 1022 | https://jira.pruconnect.net/browse/PHKLAES-1022 | [PIC] PRDA - display Monthly Annuity payment info in Financial Overview | Simon Liao | AES | 231000200-70 | because relocte format, need update sql for sequence of D8 setup | CICD ok 程序SAES AESSVC 都包括了PRDA， 看來不需要修改AES 任何程序，只要pru-life提供數據就可以了。 同時， D7 D8 的配置，也有 select * from aes_tbl_config where prod_cd = 'PRDA'; 所以不用修改程序。 20240321 Winnie need relocate format 所以update AES table sequence | Check prd | assign back to Winnie test uat | 2024-02-22 | 2024-03-01 | 2024-02-22 | 2024-02-22 | 2024-03-01
20240330 | AES | 1022 | https://jira.pruconnect.net/browse/PHKLAES-1022 | [PIC] PRDA - display Monthly Annuity payment info in Financial Overview | Simon Liao | SAES | 231000200-10 | WebContent/WEB-INF/view/proposal_policy/paymentHistory.jsp changed WebContent/WEB-INF/message/aes/locale_en.properties changed WebContent/WEB-INF/message/aes/locale_zh.properties changed | 支付記錄的wording需要修改 |  | assign back to Winnie test uat | 2024-02-22 | 2024-03-01 | 2024-02-22 | 2024-02-22 | 2024-03-01
20240330 | AES | 1024 | https://jira.pruconnect.net/browse/PHKLAES-1024 | [PIC] PRDA - Show Death Benefit Settlement Option on or after annuity period under Policy Details | Simon Liao | SAES | 231000200-10 | C:\lxw\tasks\20240330 JIRA1024\result\a037-saes\WebContent\WEB-INF\view\proposal_policy\policy_details.jsp changed src/com/pru/hk/aes/controller/policy/ProposalPolicyController.java changed src/com/pru/hk/common/util/DateUtil.java changed | CICD ok 1. add SP return value N/A check to clarify before and after annuity. 2.Add Chinese and English for PRDA description comitted to uat | ready | pending Winnie provides test data to check for start aunnuity year 20240311 Winnie: please use this test data for 1024: before annuity period: 20332529 annuity period starts: 12760725 20240314 Simon Assign back to Winnie | 2024-02-16 | 2024-03-01 | 2024-02-16 | 2024-02-16 | 2024-03-01
20240330 | AES | 1024 | https://jira.pruconnect.net/browse/PHKLAES-1024 | [PIC] PRDA - Show Death Benefit Settlement Option on or after annuity period under Policy Details | Simon Liao | AESSVC | 231000200-40 |  |  | ready | pending Winnie provides test data to check for start aunnuity year 20240311 Winnie: please use this test data for 1024: before annuity period: 20332529 annuity period starts: 12760725 20240314 Simon Assign back to Winnie | 2024-02-16 | 2024-03-01 | 2024-02-16 | 2024-02-16 | 2024-03-01
20240330 | AES | 1023 | https://jira.pruconnect.net/browse/PHKLAES-1023 | [PIC] PRDA - Add form code/letter in AES- Submitted Documents and Images | Simon Liao | AES | 231000200-40 | ARMLET-IFX/231000200-40.sh created store/231000200-40.lst created store/231000200-40.sql created | already merge to was9 |  | assign back to Winnie test uat | 2024-02-20 | 2024-03-01 | 2024-02-20 | 2024-02-20 | 2024-02-23
20240330 | AES | 1045 | https://jira.pruconnect.net/browse/PHKLAES-1045 | [PIC] Tax Letter - New doc type to be added in Submitted Documents and Images | Simon Liao | AES | 231000200-40 | store/231000200-40.sql updated | already merge to was9 |  | assign back to user |  | 2024-03-25 | 2024-03-25 | 2024-02-21 | 2024-02-23 | 2024-02-28 | 2024-02-28
20240408 | AES | 1032 | https://jira.pruconnect.net/browse/PHKLAES-1032 | [PIC Day 1.1] CIM3 - AES Future Value Illustration (FVI) | Simon Liao | AES | 220201900 | ARMLET-IFX/220201900.sh created store/220201900.lst created store/220201900.sql created | refer to JIRA1426 layout, but JIRA989 better, use shp_11.jsp, not ok, use shp_3.jsp |  | assign back to Winnie test uat not merge to uat only push and run sql 20240311 Winnie: provied 000013615503 say cannot test FVI | 2023-06-19: 2024-03-01; 2023-06-19: 2024-03-06; 2023-06-19: 2024-03-01
20240408 | AES | 1017 | https://jira.pruconnect.net/browse/PHKLAES-1017 | Update policy document images (batch 1) | Simon Liao | AES | SR02610675 | SR02610675 refer to WKFL or ODDOC, 220700800-30.sql | already push, not merge |  | assign back to Emily test uat | 2024-02-16 | 2024-02-22 | 2024-02-16 | 2024-02-21 | 2024-02-26 | 2024-03-02 | 2024-03-06 | 2024-03-07
20240408 | AES | 1018 | https://jira.pruconnect.net/browse/PHKLAES-1018 | Update policy document images (batch 2) | Simon Liao | AES | Pending for branch | SR02610675 | Pending JIRA Epic link name |  | assign back to Emily test uat | 2024-02-16 | 2024-02-22 | 2024-02-16 | 2024-02-21 | 2024-02-26 | 2024-03-02 | 2024-03-06 | 2024-03-07
2023XXXX | AES | 780 | https://jira.pruconnect.net/browse/PHKLAES-780 | [Online Enrollment] Calendar sync | Simon Liao | [5 empty] | 90% | 2023-10-09 | 2023-11-10 | 2023-10-08 |  | 2023-11-10 | 2023-11-10 |  |  | 復習記錄: 20231127 simon 1 time
2024XXXX | AES | 1021 | https://jira.pruconnect.net/browse/PHKLAES-1021 | New FVI doc type to be added in Submitted Documents and Images | Simon Liao | AES | 231000200-20 | ARMLET-IFX/231000200-20.sh created store/231000200-20.lst created store/231000200-20.sql created | merged to was9, not yet CICD, 參考最新模板JIRA1015 231000200-10.sql all channel JIRA |  | assign back to Winnie test uat | 2024-01-25 | 2024-03-01 | 2024-01-25 | 2024-01-25 | 2024-01-25
2024XXXX | AES | 1048 | https://jira.pruconnect.net/browse/PHKLAES-1048 | [PDD] Add “total premium in next anniversary year” in “My Client” | Simon Liao | SAES | 231000200-20 | src/com/pru/hk/aes/controller/policy/ProposalPolicyController.java changed WebContent/WEB-INF/message/aes/locale_en.properties changed WebContent/WEB-INF/message/aes/locale_zh.properties changed WebContent/WEB-INF/view/proposal_policy/search_client_js.jsp changed | merged to was9 already, but CI error due to holiday CI issue | ready | assign back to Winnie test uat | 2024-03-29 | 2024-03-29 | 2024-03-29 | 2024-03-29 | 2024-03-29
SR02365686

## backlog 20230331
Backlog | AES/ MYPRU | JIRA no. | JIRA Link | JIRA Title | Assign To | Repository | Branch | Changes Made | Changes Description | CI no. | CD no.
20230331 | AES | 797 | https://jira.pruconnect.net/browse/PHKLAES-797 | PIC- EGIP - AES enquiry page | Simon Liao | AES | 220700600-10 | ARMLET-IFX/220700600-10.sh store/220700600-20.sql store/220700600-10.lst |  | #39804 #39891 | 268 273
20230331 | AES | 798 | https://jira.pruconnect.net/browse/PHKLAES-798 | PIC-EGIP - AES Basic Info page | Vito Yu | SAES | 220700600-10 | WebContent/WEB-INF/view/proposal_policy/policy_details.jsp WebContent/WEB-INF/message/aes/locale_zh.propertiesM WebContent/WEB-INF/message/aes/locale_en.properties | 前端加新的关于EGIP的remark， 同时， 需要参考有EGI的代码， 部分地方就要加上EGIP | #39802 #39890 | 489 492
20230331 | AES | 798 | https://jira.pruconnect.net/browse/PHKLAES-798 | PIC-EGIP - AES Basic Info page | Vito Yu | AESSVC | 220700600-10 | src/com/pru/hk/policy/life/dao/impl/LifePolicyDaoInformixImpl.java | 需要参考有EGI的代码， 部分地方就要加上EGIP | #39805 #39881 | 492 496
20230331 | AES | 801 | https://jira.pruconnect.net/browse/PHKLAES-801 | [PIC] EGIP - Alteration Quotation | Vito Yu | SAES | N/A | N/A | 因为数据来源于prulife， 所以没修改 | N/A | N/A
20230331 | AES | 800 | https://jira.pruconnect.net/browse/PHKLAES-800 | [PIC] EGIP - Financial Overview | Heaton Liu | AES | 220700600-10 | ARMLET-IFX/220700600-10.sh created store/220700600-10.lst created store/220700600-10.sql created | 加sql insert aes_tbl_config | #39804 #39891 | 268 272
20230331 | AES | 809 | https://jira.pruconnect.net/browse/PHKLAES-809 | [PIC] EGIP- add new form for EGIP prepayment | Simon Liao | AES | 220700600-10 | store/220700600-20.sql created store/220700600-10.lst created | 加sql insert form ID | #39804 #39891 | 269 273
20230331 | AES | 813 | https://jira.pruconnect.net/browse/PHKLAES-813 | [PIC] Adding new field to AES basic info, Premium Information to display the Premium Prepayment Option | Heaton Liu | SAES | 220700600-10 | WebContent/WEB-INF/view/proposal_policy/policy_details.jsp changed WebContent/WEB-INF/message/aes/locale_en.properties changed WebContent/WEB-INF/message/aes/locale_zh.properties changed | 添加一个新字段，本来prulife写了新的sp来返回，现在不用，直接用原来的life_policy.praiInfo.prepaidDiscountPromotionFlag， 需要判断'Y' 'N' '' 三种情况 | #39802 #39890 | 489 492
20230331 | MYPRU | 1175 | https://jira.pruconnect.net/browse/PHKLMYPRUDENTIAL-1175 | [PPP220700600] PIC New Product – EGIP | Simon Liao | SESV | 220700600-10 | sv_hk/store/informix/220700600-10.sql created esv_hk/store/informix/pre-production.lst changed esv_hk/store/informix/was9_common.lst changed WebContent/WEB-INF/message/policydetail/view_en.properties changed WebContent/WEB-INF/message/policydetail/view_zh.properties changed WebContent/WEB-INF/view/mypru/policy/detail/monthly_income _table.jsp changed WebContent/WEB-INF/view/mypru/policy/detail/my_coverage.jsp changed WebContent/WEB-INF/view/mypru/policy/detail/policy_basic.jsp changed WebContent/WEB-INF/view/mypru/policy/financialSection/monthlyIncomeSection/monthlyIncome_section_master.jsp changed WebContent/WEB-INF/view/mypru/policy/financialSection/monthlyIncomeSection/monthlyIncome_section_template_c.jsp changed WebContent/WEB-INF/view/mypru/policy/financialSection/accumulationaccount.jsp changed WebContent/WEB-INF/view/mypru/policy/financialSection/basic_value.jsp changed WebContent/WEB-INF/view/mypru/policy/financialSection/cv_trad.jsp changed WebContent/WEB-INF/view/mypru/policy/financialSection/trad_policy.jsp changed | 加入新的remark for EGIP, 需要参考有EGI的代码， 部分地方就要加上EGIP | #39803 39884 | 900 923 926(SQL only)
20230331 | MYPRU | 1175 | https://jira.pruconnect.net/browse/PHKLMYPRUDENTIAL-1175 | [PPP220700600] PIC New Product – EGIP | Simon Liao | AESSVC | 220700600-10 | src/com/pru/hk/policy/life/dao/impl/LifePolicyDaoInformixImpl.javaMODIFIED changed src/com/pru/hk/policy/life/spring/bean/FinancialBusinessBean.java changed src/com/pru/hk/policy/life/to/ProdSeries.java changed | 需要参考有EGI的代码， 部分地方就要加上EGIP | #39805 跟着JIRA1158上was9 #39881 | 492 496
|  |  |  | Add refresh SI letter |  | AESSVC | 221201301-30 | a037-aessvc\src\com\pru\hk\client\life\spring\bean\EstatementBusinessBean.java changed (add SALBON in type list) a037-aessvc\src\com\pru\hk\client\eai\dao\impl\EstatementEaiDaoImpl.java changed (add SALBON in isLetterType) |  |  | waiting uat-signed-off |  |  | 2023-07-17 | 2023-08-10 | 2023-08-11
20230817 |  |  |  | PIC-PVP-add form code in AES- Submitted Documents and Image |  |  | 220700800-20 | ARMLET-IFX/220700800-20.sh store/220700800-20.lst store/220700800-20.sql | [7 empty] | 2023-08-11
20230817 | [5 empty] | AES | SR02365684 |  | 這裏第一次修改了AES庫的aes_batch， 記得CICD后需要stop and start sever AES UAT: cd /home/wasadmin/wasbin9 stopServer.sh aesuat startServer.sh aesuat ---if restart successfully, will see process id is 14811320 |  | 100% devpolyment (postponed to future) |  | 2023-06-07 | 2023-06-07 | 2023-08-07 | 2023-08-11 | 2023-08-14
[7 empty] | 230200300 |  |  |  | waiting uat-signed-off |  |  |  | 2023-08-07 | 2023-08-11
[15 empty] | 2023-08-07 | 2023-08-11
[7 empty] | SR02434383 | [8 empty] | 2023-08-11
[6 empty] | SAES | SR02365686 | [8 empty] | 2023-08-11
[6 empty] | AES | 211202200 | src/com/pru/aes/agent/db/ValueObjectConvertor.java changed | 這裏是第一次修改了AES庫的aes_src， 需要restart aesuat CR no.: CR00063030 |  | already signed off |  |  |  |  | 2023-08-11
|  | 962 | https://jira.pruconnect.net/browse/PHKLAES-962 | Claim Information - Update text in Payee if Dealth Claim | Yu Sheng Chen | SAES | IN02415015 | WebContent/WEB-INF/message/aes/locale_en.properties changed WebContent/WEB-INF/message/aes/locale_zh.properties changed WebContent/WEB-INF/view/proposal_policy/claim_history.jsp changed | 添加if语句对页面显示内容进行判断 |  | user is testing | 2023-08-10 | 2023-08-11 | 2023-08-10 | 2023-08-10 | 2023-08-11
[7 empty] | PPP/ITJR-Pending-Approval_JIRA957 |  |  |  | waiting uat-signed-off |  |  |  |  | 2023-08-11
|  |  | [PHKLMYPRUDENTIAL-1406] Support under assessment / 處理中 in Claim history - Jira (pruconnect.net) | Support under assessment / 處理中 in Claim history | Heaton Liu | SESV | PPP/ITJR-Pending-Approval_JIRA957 | WebContent/WEB-INF/view/mypru/eclaims/claimsDetails/index.jspMODIFIED | add regular expression to support "under assessment / 處理中" |  | waiting uat-signed-off | 2023-07-31 | 2023-08-02 | 2023-08-03 | 2023-08-04 | 2023-08-11
|  |  |  | [IN02365437] Enrich the error message in the registration process |  | APPSVC | IN02365437-10 |  |  |  | waiting uat-signed-off |  |  | 2023-07-17 | 2023-08-10 | 2023-08-11
[7 empty] | IN02365437 | \a074-scws\WebContent\WEB-INF\message\member\view_zh.properties changed \a074-scws\WebContent\WEB-INF\message\member\view_en.properties changed |  |  | waiting uat-signed-off |  |  | 2023-07-17 | 2023-08-10 | 2023-08-11
|  | 1407 | [PHKLMYPRUDENTIAL-1407] fix wechat batch success flag - Jira (pruconnect.net) | https://jira.pruconnect.net/browse/PHKLMYPRUDENTIAL-1407 | Alex KC Kwan | [6 empty] | 2023-08-11 | 2023-08-11 | 2023-08-11 |  | 2023-08-11
20230817 |  | 1360 | https://jira.pruconnect.net/browse/PHKLMYPRUDENTIAL-1360 | [7 empty] | 90% devpolyment (postponed to future) |  | 2023-08-07 |  | 2023-08-10 | 2023-08-11

## backlog 20230430
Backlog | AES/ MYPRU | JIRA no. | JIRA Link | JIRA Title | Assign To | Repository | Branch | Changes Made | Changes Description | CI no. | CD no.
20230430 | AES | 789 | https://jira.pruconnect.net/browse/PHKLAES-789 | PIC-POPI - AES enquiry page | Simon Liao |  | 220700700-10
20230430 | AES | 790 | https://jira.pruconnect.net/browse/PHKLAES-790 | PIC-POPI- AES Basic Info page | Heaton Liu | AES | 220700700-10 | 220700700-10.sql | 頁面上的Benefit Option and Product Feature 沒有顯示,因爲call了以下sp沒找到數據導致 policyDetailDynamicCtlList = AESFacade.getAESDynamicCtlList("policy.detail", prodCd); 只需要在加這個數據到table裏面,以上sp就會顯示數據,然而頁面就會出來了 INSERT INTO aes_tbl_config VALUES ('policy.detail','totalPremiumPaid',0,'POPI','','220700700-10',current); | 39838 | 270
20230430 | AES | 791 | https://jira.pruconnect.net/browse/PHKLAES-791 | PIC-POPI- Financial Overview | Heaton Liu |  | 220700700-10
20230430 | AES | 792 | https://jira.pruconnect.net/browse/PHKLAES-792 | PIC-POPI - AES Alteration Quotation |  |  | 220700700-10
20230430 | AES | 803 | https://jira.pruconnect.net/browse/PHKLAES-803 | PIC-POPI-add form code in AES- Submitted Documents and Images | Simon Liao | AES | 220700700-10 | 220700700-20.sql |  | 40512
20230430 | MYPRU | 1156 | https://jira.pruconnect.net/browse/PHKLPOPI-54 | [PPP220700700] PIC New Product – POPI https://jira.pruconnect.net/browse/PHKLPOPI-54 |  |  | 220700700-10
20230430 | MYPRU | 1156 | https://jira.pruconnect.net/browse/PHKLPOPI-54 | [PPP220700700] PIC New Product – POPI https://jira.pruconnect.net/browse/PHKLPOPI-55 |  |  | 220700700-10
20230430 | MYPRU | 1156 | https://jira.pruconnect.net/browse/PHKLPOPI-54 | [PPP220700700] PIC New Product – POPI https://jira.pruconnect.net/browse/PHKLPOPI-56 |  |  | 220700700-10
20230430 | MYPRU | 1156 | https://jira.pruconnect.net/browse/PHKLPOPI-54 | [PPP220700700] PIC New Product – POPI https://jira.pruconnect.net/browse/PHKLPOPI-57 |  |  | 220700700-10
20230430 | MYPRU | 1156 | https://jira.pruconnect.net/browse/PHKLPOPI-54 | [PPP220700700] PIC New Product – POPI https://jira.pruconnect.net/browse/PHKLPOPI-58 |  |  | 220700700-10
20230430 | MYPRU | 1156 | https://jira.pruconnect.net/browse/PHKLPOPI-54 | [PPP220700700] PIC New Product – POPI https://jira.pruconnect.net/browse/PHKLPOPI-59 |  |  | 220700700-10
|  |  |  | Add refresh SI letter |  | AESSVC | 221201301-30 | a037-aessvc\src\com\pru\hk\client\life\spring\bean\EstatementBusinessBean.java changed (add SALBON in type list) a037-aessvc\src\com\pru\hk\client\eai\dao\impl\EstatementEaiDaoImpl.java changed (add SALBON in isLetterType) |  |  | waiting uat-signed-off |  |  | 2023-07-17 | 2023-08-10 | 2023-08-11
20230817 |  |  |  | PIC-PVP-add form code in AES- Submitted Documents and Image |  |  | 220700800-20 | ARMLET-IFX/220700800-20.sh store/220700800-20.lst store/220700800-20.sql | [7 empty] | 2023-08-11
20230817 | [5 empty] | AES | SR02365684 |  | 這裏第一次修改了AES庫的aes_batch， 記得CICD后需要stop and start sever AES UAT: cd /home/wasadmin/wasbin9 stopServer.sh aesuat startServer.sh aesuat ---if restart successfully, will see process id is 14811320 |  | 100% devpolyment (postponed to future) |  | 2023-06-07 | 2023-06-07 | 2023-08-07 | 2023-08-11 | 2023-08-14
[7 empty] | 230200300 |  |  |  | waiting uat-signed-off |  |  |  | 2023-08-07 | 2023-08-11
[15 empty] | 2023-08-07 | 2023-08-11
[7 empty] | SR02434383 | [8 empty] | 2023-08-11
[6 empty] | SAES | SR02365686 | [8 empty] | 2023-08-11
[6 empty] | AES | 211202200 | src/com/pru/aes/agent/db/ValueObjectConvertor.java changed | 這裏是第一次修改了AES庫的aes_src， 需要restart aesuat CR no.: CR00063030 |  | already signed off |  |  |  |  | 2023-08-11
|  | 962 | https://jira.pruconnect.net/browse/PHKLAES-962 | Claim Information - Update text in Payee if Dealth Claim | Yu Sheng Chen | SAES | IN02415015 | WebContent/WEB-INF/message/aes/locale_en.properties changed WebContent/WEB-INF/message/aes/locale_zh.properties changed WebContent/WEB-INF/view/proposal_policy/claim_history.jsp changed | 添加if语句对页面显示内容进行判断 |  | user is testing | 2023-08-10 | 2023-08-11 | 2023-08-10 | 2023-08-10 | 2023-08-11
[7 empty] | PPP/ITJR-Pending-Approval_JIRA957 |  |  |  | waiting uat-signed-off |  |  |  |  | 2023-08-11
|  |  | [PHKLMYPRUDENTIAL-1406] Support under assessment / 處理中 in Claim history - Jira (pruconnect.net) | Support under assessment / 處理中 in Claim history | Heaton Liu | SESV | PPP/ITJR-Pending-Approval_JIRA957 | WebContent/WEB-INF/view/mypru/eclaims/claimsDetails/index.jspMODIFIED | add regular expression to support "under assessment / 處理中" |  | waiting uat-signed-off | 2023-07-31 | 2023-08-02 | 2023-08-03 | 2023-08-04 | 2023-08-11
|  |  |  | [IN02365437] Enrich the error message in the registration process |  | APPSVC | IN02365437-10 |  |  |  | waiting uat-signed-off |  |  | 2023-07-17 | 2023-08-10 | 2023-08-11
[7 empty] | IN02365437 | \a074-scws\WebContent\WEB-INF\message\member\view_zh.properties changed \a074-scws\WebContent\WEB-INF\message\member\view_en.properties changed |  |  | waiting uat-signed-off |  |  | 2023-07-17 | 2023-08-10 | 2023-08-11
|  | 1407 | [PHKLMYPRUDENTIAL-1407] fix wechat batch success flag - Jira (pruconnect.net) | https://jira.pruconnect.net/browse/PHKLMYPRUDENTIAL-1407 | Alex KC Kwan | [6 empty] | 2023-08-11 | 2023-08-11 | 2023-08-11 |  | 2023-08-11
20230817 |  | 1360 | https://jira.pruconnect.net/browse/PHKLMYPRUDENTIAL-1360 | [7 empty] | 90% devpolyment (postponed to future) |  | 2023-08-07 |  | 2023-08-10 | 2023-08-11

## backlog 20230223
Backlog | AES/ MYPRU | JIRA no. | JIRA Link | JIRA Title | Assign To | Repository | Branch | Changes Made | Changes Description | CI no. | CD no.
20230223 | AES | 770 | https://jira.pruconnect.net/browse/PHKLAES-770 | add form code in AES- Submitted Documents and Images | Simon Liao | AES | PPP000022120060-10 |  | 加form id SQL
20230223 | AES | 796 |  |  | Simon Liao | AES | PPP000022120060-10
| AES | 802 |  |  | Simon Liao | AES | PPP000022120060-10
20230223 | AES | 810 |  |  | Simon Liao | AES | PPP000022120060-10
20230223 | AES | 805 |  |  | Heaton Liu | SAES | PPP0000221200600
20230223 | MYPRU | 1170 | https://jira.pruconnect.net/projects/PHKLMYPRUDENTIAL/issues/PHKLMYPRUDENTIAL-1171?filter=allissues | [SR02238486] Allow corporate client to use CI no. for myPru registration | Heaton Liu | AESSVC | SR02238486 | a074-scws\WebContent\WEB-INF\message\member\view_zh.properties a074-scws\WebContent\WEB-INF\message\member\view_en.properties | 添加新的变量用于显示
20230223 | MYPRU | 1171 | https://jira.pruconnect.net/projects/PHKLMYPRUDENTIAL/issues/PHKLMYPRUDENTIAL-1171?filter=allissues | [SR02238486] Allow corporate client to use CI no. for myPru registration | Simon Liao | SCWS | SR02238486 | WebContent/WEB-INF/message/member/view_en.properties changed WebContent/WEB-INF/message/member/view_zh.properties changed | 添加新的变量用于显示
20230223 | MYPRU | 1171 | https://jira.pruconnect.net/projects/PHKLMYPRUDENTIAL/issues/PHKLMYPRUDENTIAL-1171?filter=allissues | [SR02238486] Allow corporate client to use CI no. for myPru registration | Simon Liao | APPSVC | SR02238486 | a074-appsvc\src\com\pru\hk\admin\maintmem\spring\bean\RegisterMemberBusinessBean.java a074-appsvc\src\com\pru\hk\client\eai\ClientEai.java a074-appsvc\src\com\pru\hk\client\eai\impl\ClientEaiImpl.java | APPSVC添加EAI接口直接调用prulife DB的 sql = "select client_cd from cdb_id_doc where id_no like concat(?,'%') and status = 'A'"; 返回字段给service去判断， 这样用户输入的注册id可以多查找这个sql， 如果有，就不报错说id没找到

## backlog 20230320
Backlog | AES/ MYPRU | JIRA no. | JIRA Link | JIRA Title | Assign To | Repository | Branch | Changes Made | Changes Description | CI no. | CD no.
20230320 | MYPRU | 1161 | https://jira.pruconnect.net/browse/PHKLMYPRUDENTIAL-1161 | myPRU to support oversea number (but not only accept 8 digit hk no. ) | Vito Yu | SCWS | SR02214575-support_mainland_number | src/com/pru/hk/web/controller/scws/member/EbRegistrationController.java changed WebContent/WEB-INF/view/member/registration/eb/stepEbee2.jsp changed WebContent/WEB-INF/message/member/view_en.properties changed WebContent/WEB-INF/message/member/view_zh.properties changed | 前端添加area code显示，逻辑不用修改 | 39663 | 455
20230320 | MYPRU | 1158 | https://jira.pruconnect.net/browse/PHKLMYPRUDENTIAL-1158 | Delightful Life (DL) Day 2 - add remark for SA after delightful reward has been paid | Vito Yu | SESV | 220601700 | src/com/pru/hk/mypru/adapter/ws/soap/SoapPolicySummaryAdapter.java changed src/com/pru/hk/mypru/adapter/ws/PolicySummaryAdapter.java changed src/com/pru/hk/mypru/facade/PolicySummaryFacade.java changed src/com/pru/hk/mypru/service/PolicyService.java changed src/com/pru/hk/mypru/web/controller/LifePolicyController.java changed stub/com/pru/hk/mypru/stub/policy/life/ws/PolicySummarySoapService.java changed WebContent/WEB-INF/message/mypru/view_en.properties changed WebContent/WEB-INF/message/mypru/view_zh.properties changed WebContent/WEB-INF/message/policydetail/view_en.properties changed WebContent/WEB-INF/message/policydetail/view_zh.properties changed WebContent/WEB-INF/view/mypru/policy/detail/my_coverage.jsp changed WebContent/WEB-INF/view/mypru/policy/fvi/fvi_cm_master.jsp changed WebContent/WEB-INF/view/mypru/policy/fvi/fvi_master.jsp changed WebContent/WEB-INF/view/mypru/policy/savingsProtectionRevamp.jsp changed | 对于3个JIRA提到的地方，首页saving， policy detail, FVI, 后面只有当prod_cd 是EL ELP， 还有3个条件都满足，加上remark,其中一个条件来源于prulife的一个接口，所以代码还添加了新接口用于调用这个来获取reward paid out indicator | 39884 | 923
20230320 | MYPRU | 1158 | https://jira.pruconnect.net/browse/PHKLMYPRUDENTIAL-1158 | Delightful Life (DL) Day 2 - add remark for SA after delightful reward has been paid | Vito Yu | AESSVC | 220601700 | src/com/pru/hk/policy/life/dao/impl/PolicyDaoInformixImpl.java changed src/com/pru/hk/policy/life/dao/PolicyDaoInformix.java changed src/com/pru/hk/policy/life/service/PolicySummaryService.java changed src/com/pru/hk/policy/life/spring/bean/PolicyBusinessBean.java changed src/com/pru/hk/policy/life/spring/bean/PolicyControllorBusinessBean.java changed src/com/pru/hk/policy/life/ws/soap/impl/PolicySummarySoapServiceImpl.java changed src/com/pru/hk/policy/life/ws/PolicySummarySoapService.java changed | 添加调用 call prulife@prulifeu1t:sp_chk_rtb_payout(?) 语句 | 39836 39881 | 494 496